## 011-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | add space
2 | Callout | 1 | Mohamed Ayyash | FEED/STORAGE
3 | Callout | 1 | Mohamed Ayyash | FUEL OIL/STORAGE
4 | Callout | 1 | Mohamed Ayyash | ATMOS
5 | Callout | 1 | Mohamed Ayyash | ATMOS
6 | Callout | 1 | Mohamed Ayyash | COND
7 | Callout | 1 | Mohamed Ayyash | delete (repeated)
8 | Callout | 1 | Mohamed Ayyash | ATMOS
9 | Callout | 1 | Robert.Kawitzki | What is this?
10 | Callout | 1 | Robert.Kawitzki | Drawing number required - typical comment
11 | Call-out | 1 | Sameer Foujdar | As per FEED drawing 60 psig steam is routed to convection section of Vacuum Heater to be confirmed.
12 | Text Box | 1 | Ahmed Ali | note 6
13 | Text Box | 1 | Ahmed Ali | note 6
14 | Text Box | 1 | Ahmed Ali | 6- To be used only during 7VDU by-pass to route the Atm. Resid to 6VDU/1RHCU
15 | Call-out | 1 | Ahmed Ali | change to: VAC Residue to 1RHCU feed tank
16 | Call-out | 1 | Ahmed Ali | Delete NNF
17 | Call-out | 1 | Ali Abbas | signal arrow direction
18 | Call-out | 1 | Ali Abbas | move to same location of PC0071 to better clarity and presentation.
19 | Call-out | 1 | Ali Abbas | SP location and arrow
20 | Text Box | 1 | 986131 | Please reorganize the lines and equipment. As an example Vacuum residue from flashed crude exchanger can enter the PFD from the left side and does not need to have such a long route. Follow the BMPS A8 PART D: GUIDELINES FOR PREPARING PFDs.
21 | Cloud+ | 1 | 986131 | move this to the UFD and show the flow of continuous and intermittent flows expected.
22 | Text Box | 1 | MAK | Refer to Transmittal No. BMP-MOC-TRI-00033 and drawing no. (010-A-PFD-00001-001) for General and Typical comments.
23 | Callout | 1 | alexis.martinez | Correct PC-0078 on tempered water drum: Change to PC-0072 as shown on P&ID
24 | Callout | 1 | alexis.martinez | Change on tempered water drum the vent destination to "TO ATM" instead of "TO FLARE"
25 | Text Box | 1 | alexis.martinez | General: The stream descriptors shall be "Left Justified" as in the FEED PFDs.
26 | Callout | 1 | alexis.martinez | General: Delete the Sheet no. below the connector arrow - the sheet no. shall be shown as part of the PFD drawing no shown inside the arrow e.g in this case the drawing no. shall be "010-A-PFD-00001-002"