## 016-A-MSD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Highlight | Page 1 | Salman Jaffer
2 | Callout | Page 1 | Saeed Taher
3 | Cloud | Page 1 | Mahdi Ali
4 | Microsoft Word - Code 2 Minor Comments | Page 1 | Adel
5 | Call-out | Page 1 | MAK | Always show the border size A1
6 | Callout | Page 1 | Saeed Taher | Pipe and trim material to be confirmed as per line size
7 | Callout | Page 1 | Salman Jaffer | Please explain the retinal for the discrepancy with the FEED MSD (BRB-228945), it was 1/Br
8 | Call-out | Page 1 | Mahdi Ali | Scale: NTS
9 | Call-out | Page 1 | MAK | Total Sht. shall be indicated only, 004
10 | Text Box | Page 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.