## 016-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Salman Jaffer | 3 deg Be Caustic dosing needs to be shown upstream the Electrostatic Coalescer
2 | Callout | 1 | balagangadhar.k | Avoid dog legs
3 | Callout | 1 | balagangadhar.k | Be
4 | Callout | 1 | Salman Jaffer | Correct the description to: Hydrocarbon/Caustic from C1640R to P9604 A/B/C/D
5 | Callout | 1 | Salman Jaffer | Correct the discretion to: FROM/TO P9604 A/B/C/D
6 | Callout | 1 | BD Mori | Delete the clouded text
7 | Callout | 1 | BD Mori | During FEED, based on the PFD review comments, the duty of E1603 was corrected to 1.84 MMBTU/hr. Provide rationale for again changing to original duty of 3.67 MMBUT/hr
8 | Callout | 1 | Salman Jaffer | Homogenize this PFD with other BMP units and explain these numbers (general comment)
9 | Text Box | 1 | Sang.Hwang | In psig & ID, i font shall be corrected. It looks different from others.
10 | Callout | 1 | BD Mori | Indicate the destination drawing number
11 | Callout | 1 | Salman Jaffer | Modify the description to (TO/FROM K9614 A/B discharge)
12 | Callout | 1 | balagangadhar.k | Move text to left to match with other OPC's
13 | Text Box | 1 | balagangadhar.k | NNF
14 | Text Box | 1 | balagangadhar.k | NNF
15 | Callout | 1 | Salman Jaffer | No need to retain this note (This document has been prepared base on Bapco instructions ..........)
16 | Callout | 1 | Salman Jaffer | Per BMPS A-50003, change FIC to FC and add FC full number (general comment)
17 | Callout | 1 | Salman Jaffer | Reward Note3: "This line can be used to route kerosene to 7CDU for emergency or to 1RHCU as required.
18 | Callout | 1 | Salman Jaffer | Rotating equipment data to be kept at the bottom of the page
19 | Callout | 1 | balagangadhar.k | Show Arrow at every change in direction (Typical)
20 | Callout | 1 | Salman Jaffer | Tanks numbers to be finalized based once it is finalized.
21 | Callout | 1 | Salman Jaffer | The Kerosene line from KMU to 7CDU/1RHCU needs to be relocated to P9600C Spare pump discharge instead of the P9600D per Note 3 of this sheet.
22 | Callout | 1 | Salman Jaffer | This vessel needs to be shown per BMPS A-50003
23 | Callout | 1 | Salman Jaffer | to 7CDU & 1RHCU
24 | Callout | 1 | balagangadhar.k | Update PFD number