## 018-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out |  | Ali Abbas | General comment: For consistency add arrows to signal direction.
2 | Call-out |  | Ali Abbas | Miss leading as this is block is driven by blocks of CBs logic and then through FFCs and then to FCs. Suggest adding a note.
3 | Call-out |  | Ali Abbas | Suggest stating LC 1006 A to F and delete note.
4 | Call-out |  | Ali Abbas | Suggest stating LC 1010 A to F and delete a note.
5 | Call-out |  | Ali Abbas
6 | Call-out |  | Ravi Kumar | correct Tag 018P1001 to 018P P1003
7 | Call-out |  | Ravi Kumar | The symbols delta and P are overlapping. This is a general comment
8 | Call-out |  | Ravi Kumar | Change Tag E0013 to E0020
9 | Call-out |  | Ravi Kumar | check tag no E0020 or E0026?
10 | Callout |  | alexis.martinez | The PFD Tag Number in 7VDU shown in the available PFD is BRB-228167. If there is a new TAG Number List, to be sent to all of us.
11 | Callout |  | alexis.martinez | Show the complete equipment TAG number. This apply for all the equipments.
12 | Text Box |  | MAK | Refer to General Comments in 021 - 3HDU PFD's
13 | Text Box |  | Hasan Asad | Correct: 018P1003
14 | Call-out |  | Ravi Kumar | Start-up steam heater is E0024 or E0032? General Comment: inconsistency in mark-up of tag numbers in continuation sheets. These inconsistencies will not be marked up further. To be check and corrected by JV
15 | Call-out |  | Ravi Kumar | Change Tag E0002 to E0005 on stream 128A connector
16 | Text Box |  | Ravi Kumar | CARRY OUT INTERNAL QUALITY CHECK PRIOR TO RELEASE OF DOCUMENTS FOR REVIEW. SEVERAL INCONSISTENCIES IN CONNECTORS. FEW ARE HIGHLIGHTED DURING THIS TRANSMITTAL REVIEW
17 | Highlight |  | Fatema Hashem
18 | Highlight |  | Fatema Hashem
19 | Highlight |  | Fatema Hashem
20 | Callout |  | Fatema Hashem | CORRECT THE DESCRIPTION OF LINES 172 AND 171 TO "COLD RECYCLE GAS FROM TR1 MAKE-UP COMPRESSOR DISCHARGE HEADER
21 | Callout |  | Fatema Hashem | ADD THE PDC TAG NUMBER TO THE SIGNAL DESCRIPTION. IT SHOULD BE "TO PDC 3012 ON K1001"
22 | Highlight |  | Fatema Hashem
23 | Callout |  | Fatema Hashem | CORRECT THE DESCRIPTION OF LINES 154A TO "TR1 QUENCH OIL FROM QUENCH OIL COOLER E0007"
24 | Highlight |  | Fatema Hashem
25 | Text Box |  | Fatema Hashem | GENERAL COMMENT: THE DESCRIPTION OF ALL CONNECTORS TO BE CHECKED AND CORRECTED WHERE REQUIRED. SOURCE AND DESTINATION OF EACH STREAM TO BE CHECKED AND A CLEAR DESCRIPTION TO BE ADDED.
26 | Highlight |  | Fatema Hashem
27 | Callout |  | Fatema Hashem | SHOW THE FLARE VALVE ON V1001 AS NORMALLY CLOSED (SOLID FILL)
28 | Text Box |  | Fatema Hashem | GENERAL COMMENT: ENSURE THE BATTERY LIMIT PRESSURE AND TEMPERATURE CONDITIONS ARE CONSISTENT WITH THE CONNECTING UNIT UPSTREAM OR DOWNSTREAM
29 | Highlight |  | Fatema Hashem
30 | Highlight |  | Fatema Hashem
31 | Callout |  | Fatema Hashem | CORRECT THE DESCRIPTION OF LINES 124 TO "TR1 MP/HT VAPOR TO MP/HT VAPOR/ATM COLUMN FEED EXCHANGER E0004A/B"
32 | Cloud |  | Fatema Hashem
33 | Line |  | Fatema Hashem
34 | Cloud |  | Fatema Hashem
35 | Line |  | Fatema Hashem
36 | Line |  | Fatema Hashem
37 | Highlight |  | Fatema Hashem
38 | Highlight |  | Fatema Hashem
39 | Highlight |  | Fatema Hashem
40 | Callout |  | Fatema Hashem | RE-ROUTE LINES 178/178A/171B AS SHOWN TO MINIMISE LINE CROSSING
41 | Highlight |  | Fatema Hashem
42 | Callout |  | Fatema Hashem | CORRECT THE DESCRIPTION TO "TR1 MP/HT SHORT CIRCULATION OIL (SHUTDOWN) TO SHORT CIRCULATION DRUM V0050"
43 | Text Box |  | Fatema Hashem | DEVELOP PURGE OIL PFD SIMILAR TO UTILITY FLOW DIAGRAMS SUCH THAT THE PURGE OIL FLOW AT INDIVIDUAL LOCATIONS MAY BE KNOWN
44 | Cloud |  | Fatema Hashem
45 | Callout |  | Fatema Hashem | UPDATE THE QUENCH OIL AND GAS CONNECTION AS PER THE NEW EDP. MINIMISE LINE CROSSINGS
46 | Text Box |  | Fatema Hashem | GENERAL COMMENT: ALIGN EQUIPMENT DESCRIPTION WITH THE EQUIPMENT POSITION ON THE DRAWING WHERE POSSIBLE.
47 | Stamp |  | Ranjit
48 | Text Box |  | Harshad.K.Patel | This transmittal is approved with Status Code 2. Please note that the status code 2 stamp is put only on sheet 1.. However, this stamp is applicable to all the documents within this transmittal.