## 018-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud |  | Fatema Hashem
2 | Callout |  | Fatema Hashem | MAKE THIS LINE PRIMARY THICKNESS. THIS IS THE MAIN HP LOOP PRESSURE CONTROL
3 | Cloud |  | Fatema Hashem
4 | Callout |  | Fatema Hashem | MAKE THIS LINE SECONDARY THICKNESS
5 | Cloud |  | Fatema Hashem
6 | Callout |  | Fatema Hashem | MAKE THIS LINE TERTIARY THICKNESS
7 | Callout |  | Fatema Hashem | WRITE "60# CONDENSATE"
8 | Callout |  | Fatema Hashem | CHANGE LINE 193 DESCRIPTION TO "LEAN AMINE FROM LEAN AMINE SURGE DRUM V0025"
9 | Highlight |  | Fatema Hashem
10 | Cloud |  | Fatema Hashem
11 | Callout |  | Fatema Hashem | CHANGE STREAM 131 TO PRIMARY LINE THICKNESS
12 | Highlight |  | Fatema Hashem
13 | Callout |  | Fatema Hashem | DELETE "TO"
14 | Callout |  | Fatema Hashem | CHANGE LINE 139 DESCRIPTION TO "PERMEATE TO TR1 MAKE-UP COMPRESSOR 2ND STG COMMON DISCHARGE HEADER"
15 | Highlight |  | Fatema Hashem
16 | Callout |  | Fatema Hashem | EXPAND DESCRIPTION: "EMERGENCY DEPRESSUING TO FLARE"
17 | Highlight |  | Fatema Hashem
18 | Highlight |  | Fatema Hashem
19 | Callout |  | Fatema Hashem | SHOW VALVE 8001AE AS NORMALLY CLOSED I.E. SOLID FILL
20 | Callout |  | Fatema Hashem | EXPAND DESCRIPTION: "HP LOOP DEPRESSUING TO FLARE"
21 | Highlight |  | Fatema Hashem
22 | Callout |  | Fatema Hashem | CORRECT LINE 186 DESCRIPTION TO "HP CONDENSATE FROM CONDENSATE PUMPS P0023A/B"
23 | Highlight |  | Fatema Hashem
24 | Cloud |  | Fatema Hashem
25 | Callout |  | Fatema Hashem | THIS SECTION IS TOO CROWDED. SPREAD THE EQUIPMENT AND OPTIMISE THE USE OF EMPTY SPACE