## 018-A-PFD-00001-012-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ |  | Jawad Alawi | Change numbers to new numbering system
2 | Cloud |  | Jawad Alawi
3 | Cloud |  | Jawad Alawi
4 | Cloud |  | Jawad Alawi
5 | Cloud |  | Fatema Hashem
6 | Callout |  | Fatema Hashem | DELETE SLOP LINE TO V0050 PER P&IDS
7 | Cloud |  | Fatema Hashem
8 | Callout |  | Fatema Hashem | CORRECT TO LC6001A/B
9 | Text Box |  | Fatema Hashem | GENERAL COMMENT: ALL LONG BEND LINES TO BE REPRESENTED CORRECTLY ON THE PFD.
10 | Cloud |  | Fatema Hashem
11 | Callout |  | Fatema Hashem | CORRECT XV NUMBER TO XV6026
12 | Cloud |  | Fatema Hashem
13 | Callout |  | Fatema Hashem | CORRECT REPRESENTATION OF XV6078A TO BE SIMILAR TO OTHER XV'S
14 | Cloud |  | Fatema Hashem
15 | Callout |  | Fatema Hashem | CORRECT VALVE ON XV6021A TO BALL VALVE
16 | Cloud |  | Fatema Hashem
17 | Cloud |  | Fatema Hashem
18 | Cloud |  | Fatema Hashem
19 | Cloud |  | Fatema Hashem
20 | Cloud |  | Fatema Hashem
21 | Callout |  | Fatema Hashem | CORRECT TAG TO XV6009
22 | Callout |  | Fatema Hashem | CORRECT TAG TO TI6061
23 | Callout |  | Fatema Hashem | CORRECT TAG TO TI6062
24 | Callout |  | Fatema Hashem | CORRECT LOCATION OF PI6059
25 | Callout |  | Fatema Hashem | CORRECT LOCATION OF PI6060
26 | Highlight |  | Fatema Hashem
27 | Highlight |  | Fatema Hashem
28 | Callout |  | Fatema Hashem | SHOW PI 6014
29 | Callout |  | Fatema Hashem | SHOW PI 6015
30 | Callout |  | Fatema Hashem | SHOW TI-6005
31 | Callout |  | Fatema Hashem | SHOW XV6045
32 | Cloud |  | Fatema Hashem
33 | Cloud |  | Fatema Hashem
34 | Arrow |  | Fatema Hashem
35 | Callout |  | Fatema Hashem | RE-ROUTE THE CIRCULATION COOLING OIL LINE WITH V0045A/B AND XV6044 AS SHOWN FOR SIMPLICITY
36 | Arrow |  | Fatema Hashem
37 | Callout |  | Fatema Hashem | RE-ROUTE THE SLOP OIL DRUM FEED LINE WITH XV6045 AND PC6090 AS SHOWN TO MINIMISE LINE CROSSINGS.
38 | Cloud |  | Fatema Hashem
39 | Callout |  | Fatema Hashem | CORRECT TO "XV6048A"
40 | Cloud |  | Fatema Hashem
41 | Arrow |  | Fatema Hashem
42 | Line |  | Fatema Hashem
43 | Callout |  | Fatema Hashem | RE-ROUTE THE DIESEL TO E0030 LINE TO EXIT THE PFD ON THE LEFT SIDE AND MINIMISE LINE CROSSINGS
44 | Cloud |  | Fatema Hashem
45 | Line |  | Fatema Hashem
46 | Arrow |  | Fatema Hashem
47 | Callout |  | Fatema Hashem | RE-ROUTE THE COOLING OIL LINE FROM P0025A/B AS SHOWN TO MINIMISE LINE CROSSINGS
48 | Cloud |  | Fatema Hashem
49 | Callout |  | Fatema Hashem | CORRECT TO "XV6047A"
50 | Text Box |  | Fatema Hashem | GENERAL COMMENT: SHOW LINES CARRYING CATALYST WITH PRIMARY LINE THICKNESS, SHOW OTHER LINES AND NNF LINES WITH SECONDARY LINE THICKNESS,
51 | Callout |  | Fatema Hashem | AS AN EXCEPTION, SHOW P0024A/B SPILLBACK LINE WITH CONTROL VALVE AND SIGNAL FROM FY6001
52 | Cloud |  | Fatema Hashem
53 | Callout |  | Fatema Hashem | REVIEW IF LINE TO SLOP TANKS IS REQUIRED HERE AND CROSS-CHECK WITH P&IDS