## 018-C-GAD-00011-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ahmed Bucheeri | 018E0010 | Agreed: G.A.D. has been updated accordingly, see rev_A | Y
2 | Callout | 3 | Fatema Hashem | Currently, Hastelloy cladding is shown for 10 trays i.e, from Tray 34 to 43; the Hastelloy cladding should be from Tray 33 to Tray 43. Correct the drawing sheet 3 to extend Hastelloy lining from +37135 mm el to +36600 mm elevation | Not Agreed: Mechanical data sheet is in accordance with process data sheet and with licensor EDP Doc N° (BD 143174). | N
3 | Call-out | 2 | Mahdi Ali | 2 | Agreed: G.A.D. has been updated accordingly, see rev_A | Y
4 | Call-out | 3 | Mahdi Ali | 3 | Agreed: G.A.D. has been updated accordingly, see rev_A | Y