## 018-C-GAD-00012-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Fatema Hashem | ALL CHIMNEY TRAYS TO BE NUMBERED AS PER BAPCO STANDARD
2 | Callout | 3 | Fatema Hashem | CORRECT THE LOCATION OF MANWAYS 1J AND 1K TO PROVIDE ACCESS TO THE TOP OF CHIMNEY TRAY/BOTTOM OF PACKED BED
3 | Text Box | 3 | Fatema Hashem | GENERAL COMMENT: Nozzle elevations all across the column should be representatively shown according to the elevation. Currently, some nozzles at higher elevation are shown below nozzles at lower elevation.
4 | Callout | 3 | Fatema Hashem | Nozzle 38L - Pressure tap below Bed#6 - Review elevation of this nozzle; this nozzle elevation to be just below Bed#6 and higher than Nozzles 45/46G LIT nozzles.
5 | Callout | 3 | Fatema Hashem | Location of Nozzle 40 W is shown at Tray3; it should be above Tray 4. Correct the mechanical drawing.
6 | Callout | 3 | Fatema Hashem | Nozzle 40A is shown at elevation +49700 but representatively the nozzle tapping is below Nozzle 40B shown at +49650. Check & revise depictions on the drawing.
7 | Text Box | 3 | Fatema Hashem | GENERAL COMMENT: PACKED BEDS SHALL BE PROVIDED WITH HAND-HOLES/UNLOADING ARRANGEMENT
8 | Callout | 3 | Fatema Hashem | NOZZLE 45I IS CURRENTLY SHOWN AT +1050 ELEVATION WHILE THE HHLL IS AT +1100. CORRECT SUCH THAT THE NOZZLE IS ABOVE THE HHLL.
9 | Callout | 3 | Fatema Hashem | ADVISE HOW ACCESS TO THE NOZZLE/WEAR PLATE/ BOTTOM OF CHIMNEY TRAY CAN BE ACHIEVED.
10 | Call-out | 2 | Mahdi Ali | 2
11 | Call-out | 3 | Mahdi Ali | 3
12 | Call-out | 1 | Rashed Almudahka | indicate clips weight as per FEED document
13 | Call-out | 1 | Rashed Almudahka | clarify the projection of nozzles 1J-L
14 | Call-out | 1 | Rashed Almudahka | clarify the required thickness
15 | Call-out | 3 | Rashed Almudahka | Show blind flange for manhole (nozzle 1L) similar to other manholes.