## 018-C-GAD-00013-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Fatema Hashem | HHLL is at +5570, however the level upper nozzle elevation is shown at + 4500 which is below HHLL. Review the elevation of these nozzle and move them above HHLL. | Agreed: relevant nozzles has been located @ +5800 | Y
2 | Call-out | 2 | Mahdi Ali | 2 | Agreed: G.A.D. has been updated accordingly, see rev_A | Y
3 | Call-out | 3 | Mahdi Ali | 3 | Agreed: G.A.D. has been updated accordingly, see rev_A | Y
4 | Call-out | 1 | Rashed Almudahka | Confirm vortex breaker requirement | Confirmed as required on on process data sheet
5 | Call-out | 2 | Rashed Almudahka | Confirm vortex breaker requirement. | Not Agreed: vortex breaker will be in accordance with GC-C31554 as required on process data sheet | N