## 018-E-DAT-00003-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Fatema Hashem | AS PER CLG/FEED THE CORROSION ALLOWANCE ON 18E0010 IS (3/16)IN. ADVISE THE REASON FOR THE CHANGE.
2 | Call-out | 3 | Rashed Almudahka | Add a note to cover PWHT requirement on the tube to tube-sheet joint after weld. As per OWNER reply to T598
3 | Callout | 4 | Fatema Hashem | THE TOTAL ENTHALPHY DATA ON 18E0010 IS NOT CONSISTENT WITH CLG/FEED DATASHEET. ADVISE THE SOURCE OF THIS DATA