## 018-E-DAT-00005-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Fatema Hashem | CLG SPECIFIED METALLIC FAN BLADES. ALTHOUGH BAPCO REQUESTED FOR FRP, ADVISE IF LICENSOR CONCURRENCE HAS BEEN OBTAINED TO CHANGE THE BLADE MATERIAL
2 | Callout | 2 | Fatema Hashem | GENERAL COMMENT: ENSURE THAT 18E1005 AND 18E2005 ARE IDENTICAL AND CORRECT ALL INCONSISTENCIES IN THE DATASHEETS
3 | Text Box | 2 | rob.urban | -25
4 | Text Box | 3 | rob.urban | 25. In case of loss of Feed and loss of wash water the inlet temperature may increase up to 570 F
5 | Callout | 3 | rob.urban | To get a good distribution of liquid water through all tubes, it is a must to have only one tube layer per pass
6 | Callout | 3 | rob.urban | split header box design
7 | Callout | 3 | rob.urban | This drawing is not to be followed
8 | Text Box | 3 | Sankara | Indicate applicable Hazardous Area Classification for the electric motors: Typical