## 018-G-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 3 | Hasan Asad | Relatively high
2 | Text Box | 3 | Hasan Asad | To be reviewed basis X-sec dwg.
3 | Text Box | 4 | Sankara | Temperature rise must be limited to Class B
4 | Text Box | 5 | Hasan Asad | Add: Detail preservation strategy for warehouse spare.
5 | Text Box | 6 | Hasan Asad | Capable for single train isolation.
6 | Callout | 11 | Fatema Hashem | CURRENTLY THE SEAL OIL IS SUPPLIED BY 2HCU UCO WITH A BACKUP FROM 1HCU UCO. IN CASE OF A SCENARIO WHERE ONE UNIT IS UNDERGOING CATALYST CHANGEOUT AND THE OTHER HYDROCRACKER TRIPS, SUGGEST AN ALTERNATIVE SHORT-TERM EMERGENCY SEAL OIL SOURCE IN ADDITION TO 1HCU/2HCU UCO
7 | Callout | 12 | Fatema Hashem | ADD A NOTE TO CLARIFY THE BASIS FOR THE SPECIFIED SUCTION PRESSURE
8 | Callout | 12 | Fatema Hashem | SPECIFY VAPOUR PRESSURE IN ACCORDANCE WITH LICENSOR DATASHEET
9 | Call-out | 13 | Ravi Kumar | correct outdoor storage from 12 months to 18 months (to be consistent with value stated in page 5 of 75 of this doc)
10 | Call-out | 13 | Ali Abbas | Signal is 4 to 20 mA
11 | Callout | 14 | Fatema Hashem | SPECIFY WHETHER THIS SHOULD BE DONE BY VENDOR OR EPC CONTRACTOR??
12 | Callout | 14 | Fatema Hashem | ADD A NOTE WITH 1HCU UCO LIQUID CHARACTERISTICS TO ENSURE THAT THE DESIGN TAKES INTO ACCOUNT BOTH FLUIDS
13 | Callout | 17 | Fatema Hashem | THIS IMPLIES THAT ONLY 4 FILTERS SHALL BE SUPPLIED. CORRECT TO "FOR EACH SEAL OIL SERVICE"
14 | Callout | 21 | Fatema Hashem | CORRECT REPITITION
15 | Call-out | 44 | Ali Abbas | This UPS power is from fed SRR UPSs backed up by Diesel Generator? Pls clarify
16 | Call-out | 47 | Ali Hasan | Please add the following: The I/O type and design from/to VFD and DCS shall be in compliance with the BMPS-J specifications, standard and typical drawing. The final measurement and command I/Os shall be discussed and finalized after the first design review meeting.
17 | Call-out | 48 | Ali Abbas | Need to clarify that the digital input signal to DCS will be a free volt contact through the Interposing Relay Cabinet installed at SRR. Refer to BMPS typical drawings for Interposing Relay Cabinet.
18 | Callout | 71 | Fatema Hashem | CORRECT. CHANGES TO PROCESS DATA ARE IN RED. CHANGES TO MECHANICAL DATA IS IN BLUE.
19 | Callout | 72 | Fatema Hashem | ADD ATTACHMENT NUMBER
20 | Callout | 73 | Fatema Hashem | CORRECT THE PUMPS TAG NUMBERS