## 018-K-DAT-00001-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Fatema Hashem | GENERAL COMMENT: PLEASE REFER TO BMPS-A8 SECTION 4.5.1: DO NOT INDICATE FIGURES IN EUROPEAN STYLE (WHICH USES COMMAS FOR DECIMAL POINTS AND PERIODS FOR THOUSANDS SEPARATORS), USE UK/US STYLE WITH PERIODS FOR DECIMAL PLACES AND COMMAS FOR THOUSANDS SEPARATORS. CHECK AND CORRECT ALL FIGURES
2 | Callout | 2 | Fatema Hashem | 1RHCU MAKE-UP H2 COMPRESSOR DISCHARGE PRESSURE TO BE CONSISTENT WITH THE PFD AND H&MB.
3 | Call-out | 2 | Rashed Almudahka | Updated EDP states "make-up + rec. gas". clarify inconsistency.
4 | Call-out | 15 | Rashed Almudahka | Explain the basis of 50 & 45psig air pressure
5 | Call-out | 18 | Rashed Almudahka | Clarify the basis of this value
6 | Call-out | 20 | Rashed Almudahka | clarify the requirement of modifying from FEED and updated EDP
7 | Call-out | 23 | Rashed Almudahka | clarify the requirement of modifying from FEED
8 | Text Box | 25 | Hasan Asad | The pulsation dampener shall be equipped with drain facility. This is a lesson learnt from the existing owner Refinery. The vendor/supplier shall propose automatic drain for ease of operation.
9 | Text Box | 28 | Hasan Asad | Required
10 | Text Box | 28 | Hasan Asad | Required
11 | Callout | 29 | Isamu | May be deleted as no turbine driver for these comps