## 019-A-BOD-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | A.Jabbar Mahmood | THIS DESIGN BASIS DOCUMENT (EDP CLG DESIGN BASIS WITH A COVER PAGE) IS NOT ACCEPTABLE BY OWNER AND SHALL BE RE-WRITTEN AS A NEW FRESH DOCUMENT WITH APPLICABLE INFORMATION EXTRACTED FROM THE EDP DESIGN BASIS , CHANGES MADE DURING FEED INCOPORATED AND COMMENTS MADE HEREIN IMPLEMENTED. THE DOCUMENT TO BE RE-ISSUED AND SUBMITTED FOR OWNER REVIEW.
2 | Call-out | 2 | A.Jabbar Mahmood | add "the"
3 | Call-out | 2 | A.Jabbar Mahmood | add "the"
4 | Text Box | 2 | A.Jabbar Mahmood | A TABLE OF CONTENT PAGE SHALL BE INCLUDED
5 | Text Box | 2 | A.Jabbar Mahmood | The are a number of other modifications that were carried out in the design during FEED and shall be listed. The main modifications are as follows: 1- Removal of the LP Absorber, which is supposed to treat the CLPS vapour. As part of FEED work, it has been decided to treat this stream in off-plot absorber along with other BMP gas streams. 2- During FEED, LP steam generation facility has been added on the First and Second stage reaction furnaces. Steam Superheating coils and Air preheat facility were added on the Fractionator furnace. 3- During FEED, it has been decided to have one common feed tank for both 7VDU MVGO/HVGO and 1RHCU MVGO. Hence, one cold feed line from storage will be routed to the unit. 4- Routing destination of the Product Stripper off-gas stream has been changed from SGP to 1HRU for H2 recovery. 5- In-line blending facility has been added for blending Kerosene and Heavy Naphtha into the product Diesel with the aim of maximizing diesel production within the flash point limit. Accordingly, the target rundown temperature of the final diesel stream has been changed from 120Â°F to 115Â°F.
6 | Cloud+ | 2 | A.Jabbar Mahmood | CLG's PERMISSION AND CONSENT SHALL BE OBTAINED BY TR OR TTSJV FOR REPRODUCING THEIR DOCUMENT, WHICH IS A CONFIDENTIAL PROPERTY OF CLG. TR TO CONFIRM. IT IS ALSO ASSUMED THAT A CONFIDENTIALITY AGREEMENT IS IN PLACE BETWEEN CLG AND TR. TR TO CONFIRM
7 | Cloud+ | 2 | A.Jabbar Mahmood | it shall read as "modifications"
8 | Cloud+ | 3 | A.Jabbar Mahmood | Delete - not relevant to this document
9 | Call-out | 3 | A.Jabbar Mahmood | add "...from 1RHCU"
10 | Cloud+ | 3 | A.Jabbar Mahmood | This statement is not relevant to the Design Basis document and shall be deleted.
11 | Call-out | 3 | A.Jabbar Mahmood | General to all pages: This document is now modified. TR to obtain concurrence from CLG on whether such statement can be retained.
12 | Cloud+ | 3 | A.Jabbar Mahmood | replace with "...the Design Basis"
13 | Call-out | 3 | A.Jabbar Mahmood | add "...from 7VDU"
14 | Cloud+ | 3 | A.Jabbar Mahmood | The whole section is related to the EDP scope of work and not relevant to the Design Basis document and shall be deleted.
15 | Call-out | 4 | A.Jabbar Mahmood | add "Since the Delayed Coker unit will not be in the BMP scope, the HCGO stream will not be available post BMP. The available feedstock in this case will represent the "Operating Case" and will include"
16 | Cloud+ | 4 | A.Jabbar Mahmood | Delete this statement
17 | Call-out | 4 | A.Jabbar Mahmood | add at the end "as part of the #1 Hydrogen Recovery Unit (1HRU)"
18 | Call-out | 4 | A.Jabbar Mahmood | add" ... absorber and"
19 | Cloud+ | 4 | A.Jabbar Mahmood | Delete as the stream is treated off-plot
20 | Cloud+ | 4 | A.Jabbar Mahmood | Delete as the stream is treated off-plot
21 | Cloud+ | 5 | A.Jabbar Mahmood | replace with "cold"
22 | Call-out | 5 | A.Jabbar Mahmood | Replace with "... required for supplying make-up H2 to the new diesel hydrotreating unit (3HDU) and to the new H2 plants as recycle H2"
23 | Cloud+ | 5 | A.Jabbar Mahmood | Delete - not relevant for this document
24 | Cloud+ | 5 | A.Jabbar Mahmood | Delete
25 | Cloud+ | 5 | A.Jabbar Mahmood | The product stripper off-gas stream routing has been changed to 1HRU during FEED for H2 recovery. Add a new bullet for this stream stating "Product Stripper off-gas to 1HRU".
26 | Cloud+ | 6 | A.Jabbar Mahmood | The catalyst as been changed to "AT724 1/10 AQ"
27 | Cloud+ | 7 | A.Jabbar Mahmood | Detele - not relevant to this document
28 | Cloud+ | 11 | A.Jabbar Mahmood | Delete
29 | Cloud+ | 11 | A.Jabbar Mahmood | Delete as the CLPS Vapour is not any more treated in the unit
30 | Cloud+ | 11 | A.Jabbar Mahmood | Report the properties of the untreated CLPS vapor stream (stream no.1403)
31 | Cloud+ | 27 | A.Jabbar Mahmood | Change to "Cold"
32 | Text Box | 32 | A.Jabbar Mahmood | The battery limit conditions will need to be update during EPC as the hydraulic calculations and BMP unit designs are finalized.
33 | Cloud+ | 32 | A.Jabbar Mahmood | Re-align the numbers and adjust the font size to match rest of the text. The presentation needs to be improved to the acceptable quality.
34 | Cloud+ | 32 | A.Jabbar Mahmood | Replace with "Cold"
35 | Call-out | 32 | A.Jabbar Mahmood | Add a footnote stating "The cold 7VDU HVGO and 1RHCU MVGO will be mixed in the storage tank and routed as one stream to the unit"
36 | Call-out | 33 | A.Jabbar Mahmood | add "(Process Gas)"
37 | Cloud+ | 33 | A.Jabbar Mahmood | Change to "LP Boiler Feed Water"
38 | Call-out | 33 | A.Jabbar Mahmood | add "...to be confirmed after detailed design".
39 | Cloud+ | 33 | A.Jabbar Mahmood | Report the Min/ Norm/ Max
40 | Text Box | 33 | A.Jabbar Mahmood | TABLE 7: The presentation quality of the table is not acceptable by Owner. Text and numbers shall be aligned properly with consistent font size and style. The last added row shall be shown within the table. TR may need to re-draw the whole table if needed.
41 | Call-out | 33 | A.Jabbar Mahmood | Add "The battery limit pressures will be confirmed after the detailed design"
42 | Call-out | 34 | A.Jabbar Mahmood | CLG requires at least 100Â°F superheat i.e. the temp shall be min 431Â°F. Check and confirm
43 | Call-out | 34 | A.Jabbar Mahmood | The battery limit pressure for Heavy Naphtha and Kerosene to 2HDU and 3HDU is 140 psig per the PFD. Check and update documents for consistency.
44 | Call-out | 34 | A.Jabbar Mahmood | 149°F per PFD
45 | Cloud+ | 34 | A.Jabbar Mahmood | Delete
46 | Text Box | 34 | A.Jabbar Mahmood | TABLE 8: The presentation/ information quality of the table is poor and is not acceptable by Owner. Text and numbers shall be aligned properly with consistent font size and style. The added rows shall be shown within the table. Data needs to be corrected as commented. TR will need to re-draw the whole table.
47 | Text Box | 34 | A.Jabbar Mahmood | Add a footnote on the CLPS Vapor stream indicating that "The HP Bleed stream intermittently leaves the unit battery limit "combined" with the CLPS Vapor stream"
48 | Call-out | 34 | A.Jabbar Mahmood | The B.L temp for slop is 160Â°F. Update
49 | Cloud+ | 34 | A.Jabbar Mahmood | The battery limit pressure for UCO bleed to 1RHCU is higher than 60 psig as its take-off point is u/s of the control valve. Check and update
50 | Call-out | 34 | A.Jabbar Mahmood | 450 psig per PFD. Check and update
51 | Cloud+ | 34 | A.Jabbar Mahmood | Delete. CLPS Vapour leaves unit untreated
52 | Cloud+ | 34 | A.Jabbar Mahmood | Change to 1HRU
53 | Cloud+ | 34 | A.Jabbar Mahmood | Delete
54 | Cloud+ | 34 | A.Jabbar Mahmood | Change to 1HRU
55 | Call-out | 34 | A.Jabbar Mahmood | "Compressors" plural
56 | Call-out | 34 | A.Jabbar Mahmood | The battery limit for the sour LPG is 134Â°F per the PFD. Check and update documents for consistency
57 | Cloud+ | 34 | A.Jabbar Mahmood | Delete - not applicable
58 | Call-out | 34 | A.Jabbar Mahmood | Correct the typo "Bleed". This stream is already mentioned in the table above. Amend as appropriate
59 | Call-out | 34 | A.Jabbar Mahmood | insert "for"
60 | Call-out | 34 | A.Jabbar Mahmood | insert "for"
61 | Call-out | 34 | A.Jabbar Mahmood | 113°F as per CWT PFD
62 | Cloud+ | 34 | A.Jabbar Mahmood | Change to "2HDU & 3HDU"
63 | Call-out | 34 | A.Jabbar Mahmood | Change to "2&3ARU"
64 | Call-out | 34 | A.Jabbar Mahmood | The B.L temp is 152Â°F as per PFD. Check and update
65 | Cloud+ | 34 | A.Jabbar Mahmood | The routing of stripper off-gas has been changed to 1HRU
66 | Cloud+ | 34 | A.Jabbar Mahmood | Not correct. The correct destination is "Main Cooling Water Tower"
67 | Cloud+ | 34 | A.Jabbar Mahmood | The B.L temperature is 138Â°F per the PFD. Check and update
68 | Cloud+ | 37 | A.Jabbar Mahmood | General to all pages: Delete - not relevant to this document
69 | Cloud+ | 37 | A.Jabbar Mahmood | General to all pages: This document is now modified. TR to obtain concurrence from CLG on whether their intials can be retained.
70 | Call-out | 1 | Ahmed Ali | correct the spelling to Unit
71 | Call-out | 1 | Ahmed Ali | Correct to No.2 Hydrocracking Unit
72 | Call-out | 3 | Ahmed Ali | change the sentence to: Since DCU will be built at later stage
73 | Call-out | 4 | Ahmed Ali | add: 1RHCU
74 | Call-out | 34 | Ahmed Ali | This table is not acceptable to the owner, the figures on the design basis are comments and not part of the document
75 | Cuadro de texto | 7 | fferrari | AT724 1/10 AQ
76 | Cuadro de texto | 32 | fferrari | 90
77 | Cuadro de texto | 32 | fferrari | 80
78 | Cuadro de texto | 32 | fferrari | 80
79 | Cuadro de texto | 32 | fferrari | 510
80 | Cuadro de texto | 32 | fferrari | 135
81 | Cuadro de texto | 33 | fferrari | To be confirmed
82 | Cuadro de texto | 33 | fferrari | Sweet Khuff Gas V Reaction and Fractionator Heaters 127 70
83 | Cuadro de texto | 33 | fferrari | Fractionator Heater
84 | Cuadro de texto | 33 | fferrari | TBC
85 | Cuadro de texto | 33 | fferrari | TBC
86 | Cuadro de texto | 33 | fferrari | 180
87 | Cuadro de texto | 33 | fferrari | 440
88 | Cuadro de texto | 33 | fferrari | 205
89 | Cuadro de texto | 33 | fferrari | 250
90 | Cuadro de texto | 34 | fferrari | 36
91 | Cuadro de texto | 34 | fferrari | 110
92 | Cuadro de texto | 34 | fferrari | 130
93 | Cuadro de texto | 34 | fferrari | UCO Blend V Product Fractionator 1RHCU 160 136 Make-up H2 V Make-up Compressor 3HDU 267 2633 Make-up H2 V Make-up Compressor 2HDU 267 2633
94 | Cuadro de texto | 34 | fferrari | Kerosene Inline Blending L Product Fractionator HDU 2&3 120 155 Heavy Naphtha Inline Blending L Naphtha Splitter HDU 2&3 120 147 Sour LPG L Naphtha Stabilizer Reflux Drum SGP 135 200
95 | Cuadro de texto | 34 | fferrari | 151
96 | Cuadro de texto | 34 | fferrari | 460
97 | Cuadro de texto | 34 | fferrari | 115
98 | Cuadro de texto | 34 | fferrari | 115
99 | Cuadro de texto | 34 | fferrari | 160
100 | Cuadro de texto | 34 | fferrari | 112
101 | Cuadro de texto | 34 | fferrari | 110
102 | Cuadro de texto | 34 | fferrari | 75
103 | Cuadro de texto | 34 | fferrari | 160
104 | Cuadro de texto | 34 | fferrari | 460
105 | Cuadro de texto | 34 | fferrari | 60
106 | Call-out | 34 | Hasan Al Noaimi | 2HCU
107 | Cloud+ | 3 | Jawad Alawi | Header of page 1 should be repeated for the remaining pages
108 | Cloud+ | 34 | Khalid | 110steam is LP
109 | Callout | 1 | Mohamed Ayyash | Add unit name "2HCU" apply to all pages.
110 | Callout | 1 | Mohamed Ayyash | Correct page number. Should read 1/37. Apply to all pages
111 | Callout | 1 | Mohamed Ayyash | Typo, should read "No." apply to all document.
112 | Cloud+ | 1 | Mohamed Ayyash | Delete "c" from unit number
113 | Call-out | 1 | Raj | A typical format of Basis of Design is attached herewith for consistency, to be used across BMP
114 | Call-out | 33 | Sameer Foujdar | Low pressure steam (60#) to be added to both incoming and outgoing stream table 7 and 8 respectively.