## 019-A-EQL-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 2 | A.Jabbar Mahmood | Text is not clear.
2 | Text Box | 3 | A.Jabbar Mahmood | The operating temperatures can be higher when the RCP is increased upto 730 F heater outlet (refer to heater D/S), Ensure adequancy of design temp of 019C0008 for this operating case.
3 | Text Box | 3 | A.Jabbar Mahmood | General: The hydraulic calculations have not been provided and hence owner can not verify the design and operating conditions of some of the equipment
4 | Text Box | 3 | A.Jabbar Mahmood | General: for the majority of the equipment, the reported duties in HP are not inline with the FEED D/S and P&IDS. The conversion of the power/duty from MMBtu/h to HP for the majority of the equipment seems to be in huge error. Check each single value and ensure that the conversion is done correctly.
5 | Cloud+ | 3 | A.Jabbar Mahmood | Data to be filled in
6 | Cloud+ | 3 | A.Jabbar Mahmood | The reactor outlet pressure is reported above as 2332 psig. Ensure consistency
7 | Text Box | 3 | A.Jabbar Mahmood | The operating temperatures can be higher when the RCP is increased upto 730 F heater outlet (refer to heater D/S), Ensure adequancy of design temp of 019C0007 for this operating case.
8 | Call-out | 3 | A.Jabbar Mahmood | MOC to advise the basis for the 714F design temp
9 | Cloud+ | 3 | A.Jabbar Mahmood | The TEMA type are not all consistent. Per previous Bapco's comments on MRs, both options (DEU and Modified DEU are still open for owner's selection.
10 | Text Box | 3 | A.Jabbar Mahmood | The fractionator bottoms operating temperatures can be higher when the RCP is increased. The heater outlet is designed for a higher RCP corresponding to 730 F heater outlet temperature (refer to heater D/S). MOC to review the design temperature of 019C0005 accordingly.
11 | Text Box | 3 | A.Jabbar Mahmood | The operating temperatures of the kerosene stripper are 431/489 on Max Naphtha operation mode
12 | Text Box | 3 | A.Jabbar Mahmood | General: For equipment having two units e.g E0004A/B, the reported duty for each of A and B is actually the total (A+B). To be corrected.
13 | Text Box | 3 | A.Jabbar Mahmood | The design and operating pressures of the HP pressure equipment have been generally increased significantly. CLG's conccurrence shall be obtaned.
14 | Cloud+ | 3 | A.Jabbar Mahmood | The operating temperature for E0008 is 308 F as per PFD
15 | Cloud+ | 4 | A.Jabbar Mahmood | Need to apply 10/13 rule for E0027
16 | Text Box | 4 | A.Jabbar Mahmood | 019E0002/E00021 and E0022 are all on the same circuit and can see the shutoff pressure of P0013A/B. However, the reported design pressures for each is different. Review and Update.
17 | Cloud+ | 4 | A.Jabbar Mahmood | Need to apply 10/13 rule for E0023
18 | Cloud+ | 4 | A.Jabbar Mahmood | The operating temp for E0029 is 350 F per PFD
19 | Call-out | 4 | A.Jabbar Mahmood | the operating pressure for LP BFW is 205 psig as per BMPS A1. Check and update
20 | Cloud+ | 4 | A.Jabbar Mahmood | Need to apply 10/13 rule for E0021
21 | Cloud+ | 5 | A.Jabbar Mahmood | The CW supply pressure at battery limit is 65 psig. However, some line pressure drop need to be accounted for.
22 | Cloud+ | 5 | A.Jabbar Mahmood | The operating temp in the tubeside of E0035 is 298 F for Max Naphtha mode of operation.
23 | Call-out | 5 | A.Jabbar Mahmood | 658F basis the PFD for SOR (Heater inlet). Check and update
24 | Call-out | 5 | A.Jabbar Mahmood | At this low pressure, the the level of superheat will be high possibly impacting the reboiler performance. Check and confirm
25 | Call-out | 5 | A.Jabbar Mahmood | The design temp of tubeside is 450 per FEED D/S
26 | Text Box | 9 | A.Jabbar Mahmood | Missing Data for K0001/K0002/K0003 and K0004 shall be provided
27 | Cloud+ | 9 | A.Jabbar Mahmood | The equipment name shall be change to "Secondary Ejectors"
28 | Cloud+ | 9 | A.Jabbar Mahmood | The equipment name shall be change to "Primary Ejectors"
29 | Text Box | 9 | A.Jabbar Mahmood | Data shall be filled in for the ejectors based on the package vendor input
30 | Cloud+ | 9 | A.Jabbar Mahmood | 019K0001 is Turbine driven. Update
31 | Text Box | 9 | A.Jabbar Mahmood | Data shall be filled in for the ejectors based on the vacuum package vendor input
32 | Cloud+ | 15 | A.Jabbar Mahmood | As discussed during the P&IDs review, the fractionator o/h can be see much higher temperatures (>550 F) during the start-up due to no P/A. The design temps of 019P0006A/B and P0007A/B need to be reviewed considering this operating senario.
33 | Cloud+ | 15 | A.Jabbar Mahmood | The operating temperature for 019P0009A/B is upto 487F during Max Naphtha mode of operation.
34 | Text Box | 15 | A.Jabbar Mahmood | The pump powers shall be reported
35 | Cloud+ | 16 | A.Jabbar Mahmood | General: Shall read as "PUMPAROUND" as one word.
36 | Cloud+ | 16 | A.Jabbar Mahmood | General: Spellout the word to "PUMPAROUND" and as one word.
37 | Text Box | 16 | A.Jabbar Mahmood | The operating temperatures can be higher when the RCP is increased upto 730 F heater outlet (refer to heater D/S), Ensure adequancy of design temp of Light, Heavy diesel and fractionator pumps (P0009,10,12,13,17) for this operating case.
38 | Text Box | 17 | A.Jabbar Mahmood | Provide missing data for steam turbines based on vendor input
39 | Call-out | 17 | A.Jabbar Mahmood | In page 9, the ejectors forming part of 019U0002 have been listed. The condensers which are part of the same package are not in the list. This shall be corrected.
40 | Cloud+ | 17 | A.Jabbar Mahmood | provide missing P&ID drawings
41 | Cloud+ | 18 | A.Jabbar Mahmood | provide missing data based on vendor
42 | Call-out | 18 | A.Jabbar Mahmood | The design pressure for the 1st stage surge drum to be reviewed based on the overfilling senario
43 | Cloud+ | 18 | A.Jabbar Mahmood | The operating pressure of V0018 shall be confirmed based on the interconnection hydrualics
44 | Cloud+ | 18 | A.Jabbar Mahmood | provide missing P&ID drawings
45 | Call-out | 18 | A.Jabbar Mahmood | Ensure adequacy of the design temp of V0013 during the start up when the O/H temp could reach higher than 550 F.
46 | Text Box | 18 | A.Jabbar Mahmood | The design temps of the Make-up compressors KO drums are 165 based on FEED documents. Check and update the affected documents
47 | Call-out | 18 | A.Jabbar Mahmood | The operating pressure of V0010 is 507 based on PFD. Check and update
48 | Cloud+ | 18 | A.Jabbar Mahmood | The Tan-Tan of V0018 is 2600. Check and update documents
49 | Cloud+ | 18 | A.Jabbar Mahmood | The design pressure of V0018 shall be 490 psig based on EPC bidding query T132
50 | Cloud+ | 18 | A.Jabbar Mahmood | The diameter and Tan-Tan of V0016 are 1000x2000. Check and update documents
51 | Cloud+ | 19 | A.Jabbar Mahmood | The equipment name of V0037 shall be "AMINE SUMP"
52 | Cloud+ | 19 | A.Jabbar Mahmood | Provide missing data
53 | Cloud+ | 19 | A.Jabbar Mahmood | The diameter and Tan-Tan of V0031 are 1000x2000. Check and update documents
54 | Text Box | 1 | MAK | General Comment: Use the latest document template issued to TTSJV as part of the Homogenization Procedure. The cover page shall be orientated the same as the documents they apply to.
55 | Text Box | 1 | MAK | Include HVGO FEED PUMPS 019P0029A/B/C and drivers 019T0029A/B & 019M0029C to be included in the list.
56 | Call-out | 15 | MAK | Change to (019K0002/0003/0004)
57 | Call-out | 15 | MAK | Change to (019K0001)
58 | Call-out | 18 | MAK | Change to NO.1
59 | Call-out | 18 | MAK | Change to 019OMG0001
60 | Call-out | 18 | MAK | Change to 019OMG0002
61 | Call-out | 18 | MAK | Change to NO.2
62 | Call-out | 1 | Raj | The Item Index has mainly been reviewed for the Equipment Numbering. Many design parameters cannot be checked as preceding engineering documents such as equipment datasheets, MSD etc has not been submitted/completed
63 | Call-out | 3 | Sameer Foujdar | 019DS0003 is referring to which drawing and equipment no. details to be provided.
64 | Call-out | 10 | Sameer Foujdar | Typo error spelling of BOTTOMS to be corrected
65 | Text Box | 19 | Sameer Foujdar | Please include the following in the equipment list: 1) 019P0029A/B/C 2HCU HVGO FEED PUMPS (THREE PUMPS) 2) 019M0029C 2HCU HVGO FEED PUMPS MOTOR 3) 019T0029A/B 2HCU HVGO FEED PYMPS TURBINE (TWO TURBINES) 4) 019DS0003A/B 019T0029A/B DESUPERHEATER (TWO DESUPERHEATER)
66 | Text Box | 1 | Yousif Ahmadi | General comments for all Equipment index - Use the new template - Provide Technip Group Spec. 000 GOPS 2014. - Fill the missing cells with the available information. - For new equipment in Existing units use the numbers as were agreed with Bapco.