## 019-A-MSD-00001-005-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | Correct the typos in the stream descriptors. Also ensure that the feed line are arranged in the same way they are represented in the PFDs.
2 | Call-out | 1 | A.Jabbar Mahmood | This note neither exist in the PFD nor in any design documents. A water boot is provided in the Raw feed surge drum for separating any free water which may come with the feed. TR to clarify
3 | Cloud+ | 1 | A.Jabbar Mahmood | Combine the pressure and temp as per the typical representation
4 | Call-out | 1 | A.Jabbar Mahmood | The filter package no. shall be corrected to U0001
5 | Call-out | 1 | A.Jabbar Mahmood | correct pump no. to P0011A/B
6 | Call-out | 1 | A.Jabbar Mahmood | move the injection point further to the left for clarity
7 | Call-out | 1 | A.Jabbar Mahmood | "STORAGE"
8 | Cloud+ | 1 | A.Jabbar Mahmood | Correct the line representation inline with the PFDs
9 | Call-out | 1 | Ahmed Marhoon | There is discrepancy between MSD and PID. Isolation valve and spec break are missing. Also tie-in is DS of the Control Valve. Ensure consistency between MSD, PFD & PID.
10 | Call-out | 1 | Ahmed Marhoon | There is discrepancy between MSD and PID. Isolation valve and spec break are missing. Ensure consistency between MSD, PFD & PID.
11 | Cloud+ | 1 | Ahmed Marhoon | Valve at the outlet of 19E0034 is blacked-out on PFD. Ensure consistency between MSD & PFD.
12 | Call-out | 1 | Ahmed Marhoon | Control Valve at the 19P0016 discharge is missing on MSD.
13 | Cloud+ | 1 | A.Jabbar Mahmood | The stream description shall read "UNCONVERTED OIL TO STORAGE" as per PFDs
14 | Call-out | 1 | A.Jabbar Mahmood | shall read "FEED AND PRODUCT RUNDOWN" as per PFDs