## 019-A-MSD-00001-007-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Ahmed Marhoon | Review the location of the material class break with respect to the Control Valve. Per PID, spec break is at the upstream isolation valve of Control Valve on Stripped Sour Water from 5SWS.
2 | Call-out | 1 | A.Jabbar Mahmood | The pressure is 80 psig per PFDs. Update
3 | Cloud+ | 1 | A.Jabbar Mahmood | Add the pressure and temperature indication as per the PFDs
4 | Call-out | 1 | A.Jabbar Mahmood | Shall read "2&3"
5 | Call-out | 1 | A.Jabbar Mahmood | The pressure has been updated to 50 psig per PFDs. Update
6 | Cloud+ | 1 | A.Jabbar Mahmood | shall read "RICH AMINE FROM HP H2S ABSORBER C0003"
7 | Call-out | 1 | A.Jabbar Mahmood | Add a stream dimond (stream number 1444)
8 | Call-out | 1 | A.Jabbar Mahmood | P0016A/B
9 | Cloud+ | 1 | A.Jabbar Mahmood | Shall read "INJECTION WATER TO E0007B/E0008"
10 | Call-out | 1 | A.Jabbar Mahmood | P0022A/B
11 | Cloud+ | 1 | A.Jabbar Mahmood | Adjust the font for clarity (typical)
12 | Call-out | 1 | A.Jabbar Mahmood | P0028A/B
13 | Call-out | 1 | A.Jabbar Mahmood | "COLD CONDENSATE..."
14 | Callout | 1 | Yousif Ahmadi | In FEED it is S-5. Specify the basis of this change
15 | Callout | 1 | Yousif Ahmadi | Specify the basis of this change
16 | Callout | 1 | Yousif Ahmadi | Add line Spec.