## 019-C-GAD-00003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | A.Jabbar Mahmood | CLG's detailed mechanical drawing with the "Fabrication notes" in RD-140630 shall be included when the vendor is selected,
2 | Text Box | 1 | Mahdi Ali | remove 'c' from unit number
3 | Text Box | 1 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
4 | Text Box | 1 | MAK | Use the latest drawing borders as in BMPS-A-50009 Rev. 1 dated 09-04-2018.
5 | Call-out | 1 | MAK | 019 - NO. 2 HYDROCRACKING UNIT
6 | Cloud+ | 1 | A.Jabbar Mahmood | According to the P&IDs and FEED D/S, the rating is 1500#. Check and confirm
7 | Cloud+ | 1 | Jawad Alawi | Confirm material type. Swap shell and heads spec
8 | Call-out | 1 | Sameer Foujdar | Pleases include note 25 in the notes.
9 | Cloud+ | 1 | bapco-user | Materials Spec. are missing for Ladder & Platform Support/ Piping support
10 | Cloud+ | 1 | bapco-user | CA is not as per Note 18 in Page 2 of 3 and FEED Drwg
11 | Callout | 1 | bapco-user | What about Nozzle Flange (Size <=6)
12 | Callout | 1 | bapco-user | Correct: SA 194 GR 8CA
13 | Text Box | 1 | A.Jabbar Mahmood | This drawing shall be reviewed and approved by the Licensor
14 | Text Box | 2 | Mahdi Ali | remove 'c' from unit number
15 | Text Box | 2 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
16 | Callout | 2 | Mohamed Ayyash | Allign
17 | Call-out | 2 | Sameer Foujdar | It is separator not reactor
18 | Text Box | 3 | Mahdi Ali | Use latest border that includes a different disclaimer note.
19 | Text Box | 3 | Mahdi Ali | remove 'c' from unit number
20 | Text Box | 3 | Mahdi Ali | This shall be sheet 1 of 3
21 | Text Box | 3 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
22 | Text Box | 3 | Mahdi Ali | 1. Always put the general arrangement as sheet 1. 2. Indicate the equipment number inside the equipment.