## 019-C-GAD-00004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | The operating pressure as per the FEED "process" D/S and Licensor is 2200 psig. Correct it if it is a typo. If it has been revised, owner needs the hydraulic calc to verify it. CLG needs to be advised. | Noted, it will be updated at revision A | Y
2 | Cloud+ | 1 | A.Jabbar Mahmood | It is not clear why this specific nozzle has a higher rating than others for the same vessel. It is 1500# a per FEED D/S and P&IDs. Check and verify | Design Temperature of bottom Product Stripper from 543ºF to 714ºF | N
3 | Callout | 1 | Mohamed Ayyash | General comment for all GAD drawings in this Document Typo, delete c | Noted, it will be updated at revision A | Y
4 | Callout | 1 | Mohamed Ayyash | General comment for all GAD drawings in this Document Move unit name to center of cell for better representation | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
5 | Text Box | 1 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
6 | Text Box | 1 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
7 | Text Box | 1 | MAK | 3 | Noted, it will be updated at revision A | Y
8 | Text Box | 1 | Ahmed Marhoon | Location of nozzles for the level instruments shall be firmed post detail design/Hazop/SIL by the TTSJV taking into account the hold-up volume/surge volume and residence time specified under section 7.6 of the BMPS-A3. This is a typical comment for all vessels/columns with level measurement (control and ESD). | Noted, included at note 25 | N
9 | Text Box | 1 | Mahdi Ali | Add drawing | Noted, it will be updated at revision A | Y
10 | Callout | 1 | Yousif Ahmadi | SA 194-2H | As per standard BMPS-SD-E-10286, where is a danger of sulphide stress corrosion cracking, use type 4 bolting (A193 Gr.B7M & A194 Gr.2M) | N
11 | Text Box | 2 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
12 | Text Box | 2 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
13 | Call-out | 2 | MAK | 2 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
14 | Text Box | 2 | Mahdi Ali | Resolve Overlap issue | Noted, it will be updated at revision A | Y
15 | Cloud+ | 3 | A.Jabbar Mahmood | The bottom of the coalescer pad shall shown on the same elevation as the LLIL as per the process datasheet. | Noted, it will be updated at revision A | Y
16 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing RC-940132 | Noted, it will be updated at revision A | Y
17 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing GC-C31554 | Noted, it will be updated at revision A | Y
18 | Text Box | 3 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
19 | Text Box | 3 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
20 | Call-out | 3 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
21 | Cloud+ | 3 | Ahmed Marhoon | Review the elevation of N5B in view of the LLLL. | N5B elevation is on HOLD, instrumentation department is checking this elevation | N
22 | Text Box | 3 | Mahdi Ali | Add Equipment number in the drawing | Already indicated at page 1 | N