## 019-C-GAD-00006-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
2 | Text Box | 1 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
3 | Text Box | 1 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
4 | Call-out | 1 | Sameer Foujdar | Design temperature for all the three elements heads, shell is 174 F as per the data sheet. The temperature mentioned here is 308 F to be checked and confirmed. | Design temperature has changes, see Process data sheet | N
5 | Call-out | 1 | Ahmed Marhoon | Add the typical HOLD note for the instrument nozzles. Type, size, number and location to be finalized post detail design development and Hazop3/SIL sessions. | indicated at note 23 | N
6 | Text Box | 1 | Ahmed Marhoon | Location of nozzles for the level instruments shall be firmed post detail design/Hazop/SIL by the TTSJV taking into account the hold-up volume/surge volume and residence time specified under section 7.6 of the BMPS-A3. This is a typical comment for all vessels/columns with level measurement (control and ESD). | included at note 23 | N
7 | Text Box | 1 | Mahdi Ali | Add DRAWING | Noted, it will be updated at revision A | Y
8 | Callout | 1 | Yousif Ahmadi | SA 194-2H | As per standard BMPS-SD-E-10286, where is a danger of sulphide stress corrosion cracking, use type 4 bolting (A193 Gr.B7M & A194 Gr.2M) | N
9 | Cloud+ | 1 | Yousif Ahmadi | Per FEED document this is SELF-REIF. Check and confirm | LWN Type is an integrally selfreinforced nozzle | N
10 | Callout | 1 | Yousif Ahmadi | Nozzle from pipe: SA 106 GR BN | there are no nozzles from pipe | N
11 | Cloud+ | 1 | Yousif Ahmadi | Per FEED document all SA 516 are of grade 70 | For Wet H2S service SA 516 Gr 60 as per BMPS-A26 | N
12 | Text Box | 2 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
13 | Text Box | 2 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
14 | Call-out | 2 | MAK | 2 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
15 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing RC-940132 | Noted, it will be updated at revision A | Y
16 | Cloud+ | 3 | A.Jabbar Mahmood | The dimension is 1525 mm as per Licensor D/S. Confirm | Noted, it will be updated at revision A | Y
17 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing GC-C31554 | Noted, it will be updated at revision A | Y
18 | Text Box | 3 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
19 | Text Box | 3 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
20 | Call-out | 3 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
21 | Cloud+ | 3 | Ahmed Marhoon | Review the elevation of N5A. To be at the same elevation of the N4A to cover the same range/span. | N5A Elevation is on hold, instrumentation is checking these elevations | N
22 | Text Box | 3 | Mahdi Ali | Add equipment number in the drawing | It's indicated at first page | N