## 019-C-GAD-00006-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest A3 Border
2 | Text Box | 1 | MAK | 019 - 2HCU
3 | Text Box | 1 | MAK | 3
4 | Call-out | 1 | Sameer Foujdar | Design temperature for all the three elements heads, shell is 174 F as per the data sheet. The temperature mentioned here is 308 F to be checked and confirmed.
5 | Call-out | 1 | Ahmed Marhoon | Add the typical HOLD note for the instrument nozzles. Type, size, number and location to be finalized post detail design development and Hazop3/SIL sessions.
6 | Text Box | 1 | Ahmed Marhoon | Location of nozzles for the level instruments shall be firmed post detail design/Hazop/SIL by the TTSJV taking into account the hold-up volume/surge volume and residence time specified under section 7.6 of the BMPS-A3. This is a typical comment for all vessels/columns with level measurement (control and ESD).
7 | Text Box | 1 | Mahdi Ali | Add DRAWING
8 | Callout | 1 | Yousif Ahmadi | SA 194-2H
9 | Cloud+ | 1 | Yousif Ahmadi | Per FEED document this is SELF-REIF. Check and confirm
10 | Callout | 1 | Yousif Ahmadi | Nozzle from pipe: SA 106 GR BN
11 | Cloud+ | 1 | Yousif Ahmadi | Per FEED document all SA 516 are of grade 70
12 | Text Box | 2 | MAK | Use the latest A3 Border
13 | Text Box | 2 | MAK | 019 - 2HCU
14 | Call-out | 2 | MAK | 2
15 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing RC-940132
16 | Cloud+ | 3 | A.Jabbar Mahmood | The dimension is 1525 mm as per Licensor D/S. Confirm
17 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing GC-C31554
18 | Text Box | 3 | MAK | Use the latest A3 Border
19 | Text Box | 3 | MAK | 019 - 2HCU
20 | Call-out | 3 | MAK | 3
21 | Cloud+ | 3 | Ahmed Marhoon | Review the elevation of N5A. To be at the same elevation of the N4A to cover the same range/span.
22 | Text Box | 3 | Mahdi Ali | Add equipment number in the drawing