## 019-C-GAD-00009-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
2 | Text Box | 1 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
3 | Text Box | 1 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
4 | Call-out | 1 | Ahmed Marhoon | Add the typical HOLD note for the instrument nozzles. Type, size, number and location to be finalized post detail design development and Hazop3/SIL sessions. | indicated at note 24 | N
5 | Text Box | 1 | Ahmed Marhoon | Location of nozzles for the level instruments shall be firmed post detail design/Hazop/SIL by the TTSJV taking into account the hold-up volume/surge volume and residence time specified under section 7.6 of the BMPS-A3. This is a typical comment for all vessels/columns with level measurement (control and ESD). | included in note 24 | N
6 | Text Box | 1 | Mahdi Ali | Add DRAWING | Noted, it will be updated at revision A | Y
7 | Callout | 1 | Yousif Ahmadi | Nozzle from pipe: SA 106 GR BN | there are no nozzles from pipe | N
8 | Callout | 1 | Yousif Ahmadi | SA 194-2H | As per standard BMPS-SD-E-10286, where is a danger of sulphide stress corrosion cracking, use type 4 bolting (A193 Gr.B7M & A194 Gr.2M) | N
9 | Callout | 1 | Yousif Ahmadi | Per FEED document design pressure is 2303. | New data from Process data sheet | N
10 | Call-out | 2 | A.Jabbar Mahmood | Note 17: Also report N2 and water as per the process datasheet | Noted, it will be updated at revision A | Y
11 | Text Box | 2 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
12 | Text Box | 2 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
13 | Call-out | 2 | MAK | 2 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
14 | Cloud+ | 2 | Yousif Ahmadi | Fixed internal CA is 4.8 per FEED document and table in the first page of this document | 6.4 total CA as per specifications | N
15 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing RC-940132 | Noted, it will be updated at revision A | Y
16 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing GC-C31554 | Noted, it will be updated at revision A | Y
17 | Call-out | 3 | A.Jabbar Mahmood | The dimension is 1050 mm i.e. 1/2 the ID as per the FEED and Licensor D/S. | Noted, it will be updated at revision A | Y
18 | Text Box | 3 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
19 | Text Box | 3 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
20 | Call-out | 3 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
21 | Text Box | 3 | Mahdi Ali | Add equipment number in the drawing | Already indicated at sheet 1 | N