## 019-C-GAD-00010-001-RAP-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
2 | Text Box | 1 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated.
3 | Text Box | 1 | MAK | Use the latest drawing borders as in BMPS-A-50009 Rev. 1 dated 09-04-2018. | Agreed.
4 | Call-out | 1 | MAK | 019 - NO. 2 HYDROCRACKING UNIT | Agreed, included and updated.
5 | Cloud+ | 1 | A.Jabbar Mahmood | The design and operating pressure is significantly higher than those in the FEED D/S and Licensor D/S (by about 23 psi). TR to provide the basis for this change. Also, CLG shall be consulted/ notified for this change in design and operating conditions. | The Section of Process has informed that they are waiting answer from Chevron to make them official.
6 | Cloud+ | 1 | A.Jabbar Mahmood | N1 size is 12" as per FEED D/S and P&IDs. Check and confirm | Agreed, this was corrected and updated.
7 | Call-out | 1 | A.Jabbar Mahmood | N3 size is 6" as per FEED D/S. Verify | Verified, this size is as per Process DDSS.
8 | Call-out | 1 | Sameer Foujdar | Corrosion allowance refers to note no 14 in the general notes not to note 16,17. | Agreed, this was corrected and updated.
9 | Cloud+ | 1 | bapco-user | CA is not as per Note 14 in Page 2 of 3 and FEED Drwg | The CA is indicated in that table for shell and head, internally (WOL) and externally (1,5 mm). The Note 14 indicates the CA for fixed and removable internals.
10 | Cloud+ | 1 | bapco-user | Nozzles per FEED is SA 335 P11 + WOL. Please specify the reason of this change. | Because all equipments nozzles have been specified as self reinforced, this means that material has to be forged, SA-335 refers to seamless pipe, which it is not forged material.
11 | Cloud+ | 1 | bapco-user | This should be 80 or 280?? | It is 80 instead of 280, this was a typo error, this has already corrected and updated.
12 | Text Box | 2 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
13 | Text Box | 2 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated.
14 | Cloud+ | 2 | A.Jabbar Mahmood | The Max H2 partial pressure is not consistent with the reported operating pressure (530 psig) - Also refer to the comment in sheet 1. | See answer to comment no. 5
15 | Call-out | 2 | Sameer Foujdar | It is separator not reactor | Agreed, corrected and updated.
16 | Cloud+ | 2 | bapco-user | Note 13: change 019V0007 to 019V0010 | Agreed, this was corrected and updated.
17 | Text Box | 3 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
18 | Text Box | 3 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated.
19 | Text Box | 3 | Mahdi Ali | 1. Always put the general arrangement as sheet 1. 2. Indicate the equipment number inside the equipment. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
20 | Text Box | 3 | Mahdi Ali | Use latest border that includes a different disclaimer note. | Agreed.
21 | Call-out | 3 | Ahmed Marhoon | Improve drafting by showing LLL at a higher elevation than N5A/N5C Nozzles. | Agreed, corrected and updated.
22 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing RC-940132 | Agreed, included and updated.