## 019-C-GAD-00010-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
2 | Text Box | 1 | Mahdi Ali | remove 'c' from unit number
3 | Text Box | 1 | MAK | Use the latest drawing borders as in BMPS-A-50009 Rev. 1 dated 09-04-2018.
4 | Call-out | 1 | MAK | 019 - NO. 2 HYDROCRACKING UNIT
5 | Cloud+ | 1 | A.Jabbar Mahmood | The design and operating pressure is significantly higher than those in the FEED D/S and Licensor D/S (by about 23 psi). TR to provide the basis for this change. Also, CLG shall be consulted/ notified for this change in design and operating conditions.
6 | Cloud+ | 1 | A.Jabbar Mahmood | N1 size is 12" as per FEED D/S and P&IDs. Check and confirm
7 | Call-out | 1 | A.Jabbar Mahmood | N3 size is 6" as per FEED D/S. Verify
8 | Call-out | 1 | Sameer Foujdar | Corrosion allowance refers to note no 14 in the general notes not to note 16,17.
9 | Cloud+ | 1 | bapco-user | CA is not as per Note 14 in Page 2 of 3 and FEED Drwg
10 | Cloud+ | 1 | bapco-user | Nozzles per FEED is SA 335 P11 + WOL. Please specify the reason of this change.
11 | Cloud+ | 1 | bapco-user | This should be 80 or 280??
12 | Text Box | 2 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
13 | Text Box | 2 | Mahdi Ali | remove 'c' from unit number
14 | Cloud+ | 2 | A.Jabbar Mahmood | The Max H2 partial pressure is not consistent with the reported operating pressure (530 psig) - Also refer to the comment in sheet 1.
15 | Call-out | 2 | Sameer Foujdar | It is separator not reactor
16 | Cloud+ | 2 | bapco-user | Note 13: change 019V0007 to 019V0010
17 | Text Box | 3 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
18 | Text Box | 3 | Mahdi Ali | remove 'c' from unit number
19 | Text Box | 3 | Mahdi Ali | 1. Always put the general arrangement as sheet 1. 2. Indicate the equipment number inside the equipment.
20 | Text Box | 3 | Mahdi Ali | Use latest border that includes a different disclaimer note.
21 | Call-out | 3 | Ahmed Marhoon | Improve drafting by showing LLL at a higher elevation than N5A/N5C Nozzles.
22 | Call-out | 3 | A.Jabbar Mahmood | Reference shall be made to the licensor standard drawing RC-940132