## 019-C-GAD-00011-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Delete extended lines
2 | Callout | 1 | bapco-user | Ext. STUD B. NUTS: It should be SA 194 2H per FEED document
3 | Callout | 1 | Mohamed Ayyash | Align
4 | Cloud+ | 1 | A.Jabbar Mahmood | AS per FEED D/S, it is 6" in size. Verify
5 | Callout | 1 | Mohamed Ayyash | Overlap "correct"
6 | Callout | 1 | Mohamed Ayyash | Move to center of cell (on all the 3 sheets)
7 | Callout | 1 | Mohamed Ayyash | Delete c (on all the 3 sheets)
8 | Cloud+ | 2 | A.Jabbar Mahmood | The Max H2 PP Shall be 439 psia (0.875 x (487+14.7)). Verify
9 | Cloud+ | 2 | Ahmed Marhoon | document number to be confirmed.