## 019-C-GAD-00028-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Adnan Alothman | Add "-" to the Ext. Design Pressure (-10).
2 | Callout | 1 | Mohamed Ayyash | Overlap "correct"
3 | Callout | 1 | Mohamed Ayyash | Delete c (on all the 3 sheets)
4 | Callout | 1 | Mohamed Ayyash | Move to center of cell (on all the 3 sheets)
5 | Callout | 1 | Mohamed Ayyash | Align
6 | Callout | 1 | bapco-user | Ext. STUD B. NUTS: It should be SA 194 2H per FEED document
7 | Callout | 2 | bapco-user | Correct typo error: IMMISCIBLE
8 | Text Box | 2 | A.Jabbar Mahmood | It is suggested that the maximum H2S is reported as a note.
9 | Cloud+ | 3 | A.Jabbar Mahmood | The "min" shall be instead applied for the vapour outlet nozzle (N2) as per FEED process datasheet and Licensor D/S, unless the nozzle numbering is in error i.e. N2 is supposed to b N6 and vis versa. Check and confirm
10 | Cloud+ | 3 | A.Jabbar Mahmood | Reference shall be made to the Licensor Oil Skim standard drawing (GB-C15110)