## 019-C-GAD-00029-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Move to center of cell (on all the 4 sheets)
2 | Cloud+ | 1 | bapco-user | Per FEED drawing the following are Nace Shell Head Flange & Blind Self reinforcing nozzle neck check and confirm
3 | Callout | 1 | bapco-user | Ext. STUD B. NUTS: It should be SA 194 2H per FEED document
4 | Callout | 1 | Mohamed Ayyash | Align
5 | Call-out | 1 | Ahmed Marhoon | Notes 21 and 22 on Sheet 2 of 019-C-GAD-00028-001 are also applicable for Nozzles N7A-D. Notes to be added accordingly.
6 | Callout | 1 | Mohamed Ayyash | Delete c (on all the 4 sheets)
7 | Cloud+ | 1 | Adnan Alothman | Add "-" to the Ext. Design Pressure (-10).
8 | Call-out | 2 | Ahmed Marhoon | Stilling well requirement and design to be confirmed/finalized with level measurement vendor. Typical comment.
9 | Text Box | 2 | A.Jabbar Mahmood | It is suggested that the maximum H2S is reported as a note.
10 | Cloud+ | 2 | Ahmed Marhoon | Note 7 to be corrected.
11 | Cloud+ | 2 | A.Jabbar Mahmood | Correct the equipment number as per the new numbering
12 | Cloud+ | 3 | A.Jabbar Mahmood | Increase the size of the internal part proportionally for better representation
13 | Call-out | 3 | Ahmed Marhoon | Add "HOLD" to the level nozzles elevations. Typical