## 019-C-GAD-10003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
2 | Text Box | 1 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
3 | Call-out | 1 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
4 | Text Box | 1 | MAK | 4 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
5 | Call-out | 1 | Ahmed Marhoon | Add the typical HOLD note for the instrument nozzles. Type, size, number and location to be finalized post detail design development and Hazop3/SIL sessions. | Noted, it will be updated at revision A | Y
6 | Text Box | 1 | Ahmed Marhoon | Location of nozzles for the level instruments shall be firmed post detail design/Hazop/SIL by the TTSJV taking into account the hold-up volume/surge volume and residence time specified under section 7.6 of the BMPS-A3. This is a typical comment for all vessels/columns with level measurement (control and ESD). | Noted, it will be updated at revision A | Y
7 | Text Box | 1 | Mahdi Ali | Add DRAWING | Noted, it will be updated at revision A | Y
8 | Cloud+ | 1 | Yousif Ahmadi | Per FEED datasheet this is 8" | Nozzle size has changed, see Process data sheet | N
9 | Cloud+ | 1 | Yousif Ahmadi | Per FEED document this is SELF. Reinf. | LWN Type is an integrally selfreinforced nozzle | N
10 | Callout | 1 | Yousif Ahmadi | Per FEED document design pressure is 2310 and temperature is 178. Check and confirm | It has changed, see Process data sheet | N
11 | Text Box | 2 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
12 | Text Box | 2 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
13 | Call-out | 2 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
14 | Call-out | 2 | MAK | 2 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
15 | Cloud+ | 3 | A.Jabbar Mahmood | The gap between the demister pad edge and the column wall is 200 mm as per the FEED D/S and hence the demister dia shall be 2494 mm instead. Check and confirm. | Noted, it will be updated at revision A | Y
16 | Text Box | 3 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
17 | Text Box | 3 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
18 | Call-out | 3 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
19 | Call-out | 3 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
20 | Cloud+ | 3 | Ahmed Marhoon | HLL elevation shall be within the level measurement span. Currently the upper level nozzle is located lower (+2920) than the HLL (+2970) which need to be corrected. | level nozzle instruments elevation are on hold, instrumentation department is checking these elevations | N
21 | Text Box | 3 | Mahdi Ali | Add equipment number in the drawing | Already indicated at sheet 1 | N
22 | Cloud+ | 4 | A.Jabbar Mahmood | The MIN is applicable to for the distance between the pipe and the column wall. Correct the representation. | Noted, it will be updated at revision A | Y
23 | Cloud+ | 4 | A.Jabbar Mahmood | Improve the representation of the distances between the lines inline with the drawing below this view e.g the downcomer width is shown here much narrower than in the drawing below. | This is an sketch, do not scale. Detailed drawing will be provided by Vendor | N
24 | Text Box | 4 | MAK | Use the latest A3 Border | Noted, it will be updated at revision A | Y
25 | Text Box | 4 | MAK | 019 - 2HCU | Noted, it will be updated at revision A | Y
26 | Call-out | 4 | MAK | 3 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
27 | Call-out | 4 | MAK | 4 | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables | N
28 | Text Box | 4 | Mahdi Ali | Add equipment number in the drawing | Already indicated at sheet 1 | N