## 019-C-GAD-10005-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | "FROM"
2 | Call-out | 1 | MAK | 5
3 | Call-out | 2 | MAK | 5
4 | Call-out | 3 | MAK | 5
5 | Call-out | 2 | MAK | 2
6 | Text Box | 1 | MAK | 3
7 | Call-out | 3 | MAK | 3
8 | Text Box | 1 | MAK | 019 - 2HCU
9 | Text Box | 2 | MAK | 019 - 2HCU
10 | Text Box | 3 | MAK | 019 - 2HCU
11 | Call-out | 1 | A.Jabbar Mahmood | 1.9e+18
12 | Call-out | 1 | A.Jabbar Mahmood | 1.9e+22
13 | Call-out | 1 | A.Jabbar Mahmood | 1.9e+28
14 | Call-out | 1 | A.Jabbar Mahmood | 019P0006A/B
15 | Call-out | 1 | A.Jabbar Mahmood | 019P0008A/B
16 | Call-out | 1 | A.Jabbar Mahmood | 019P0010A/B
17 | Call-out | 1 | A.Jabbar Mahmood | 019P0010A/B
18 | Call-out | 1 | A.Jabbar Mahmood | 019P0012A/B
19 | Call-out | 1 | A.Jabbar Mahmood | 019P0012A/B
20 | Call-out | 1 | A.Jabbar Mahmood | 019P0017A/B
21 | Text Box | 1 | A.Jabbar Mahmood | Correct the referenced equipment numbers under the "SERVICE" column as per the new equipment numbering, as indicated.
22 | Cloud+ | 1 | Yousif Ahmadi | Efficiency is 1 per FEED data sheet. Check and confirm
23 | Cloud+ | 1 | A.Jabbar Mahmood | Indicate the ext design pressures in "Negative" values
24 | Cloud+ | 2 | A.Jabbar Mahmood | Indicate the reference for this note in the drawing
25 | Cloud+ | 1 | Yousif Ahmadi | Per FEED data sheet should be of grade 70
26 | Text Box | 3 | A.Jabbar Mahmood | There are a number of important details missing in the drawings. It is suggested that "Details A to K" presented in the process d/s be included in the mechanical drawing
27 | Cloud+ | 3 | A.Jabbar Mahmood | TR to verify if tray# 34 shall have seal pans. May need CLG's confirmation.
28 | Text Box | 1 | MAK | Use the latest A3 Border
29 | Text Box | 2 | MAK | Use the latest A3 Border
30 | Text Box | 3 | MAK | Use the latest A3 Border