## 019-C-GAD-10009-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page 1 | MAK | 9
2 | Call-out | Page 2 | MAK | 9
3 | Call-out | Page 3 | MAK | 9
4 | Call-out | Page 2 | MAK | 2
5 | Text Box | Page 1 | MAK | 3
6 | Call-out | Page 3 | MAK | 3
7 | Text Box | Page 1 | MAK | 019 - 2HCU
8 | Text Box | Page 2 | MAK | 019 - 2HCU
9 | Text Box | Page 3 | MAK | 019 - 2HCU
10 | Call-out | Page 1 | MAK | GAD
11 | Cloud+ | Page 1 | A.Jabbar Mahmood | Indicate "negative" values for the ext design pressures.
12 | Callout | Page 3 | Yousif Ahmadi | Per FEED data sheet thickness is 23 mm. check and confirm
13 | Text Box | Page 3 | A.Jabbar Mahmood | There are a number of important details missing in the drawings. It is suggested that "Details A to B" presented in the process d/s be included in the mechanical drawing
14 | Text Box | Page 1 | MAK | Use the latest A3 Border
15 | Text Box | Page 2 | MAK | Use the latest A3 Border
16 | Text Box | Page 3 | MAK | Use the latest A3 Border