## 019-C-GAD-10010-001-RAP
ID N. | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco Closure (Y/N)
1 | Callout | A.Jabbar Mahmood | Typo in the title: NAPHTHA SPLITTER
2 | Callout | A.Jabbar Mahmood | External design pressures shall be reported as negative values (vacuum) i.e. as -10 psig
3 | Text Box | A.Jabbar Mahmood | A note should be added indicating that the sizes of the column nozzles may change during the development of the detailed design.
4 | Callout | alexis.martinez | The equipment TAG number and the description shall be shown in all the sheets.
5 | Cloud+ | Ahmed Marhoon | The current revision indicates the instrumention connections based on the current PID revision. Vendor shall be notified on the possibility of having more connections (especially for the level instruments) after design development and post-Hazop3. E.g. if a trip command is envisaged per Hazop/SIL studies, then new tappings will need to be provided for the ESD LITs to meet the specifications. This is typical comment for all equipment data sheets across BMP units.
6 | Call-out | Ahmed Marhoon | Add Unit Name according to the WBS: for this case (2HCU)
7 | Callout | A.Jabbar Mahmood | TYPO in Note 22: drop
8 | Callout | A.Jabbar Mahmood | Use "dot" for decimal point.
9 | Cloud+ | Ahmed Marhoon | Based to the PID, EDP's GAD and to avoid dead-legs in the level bridle, lower level tapping (45B) needs to be relocated to the side of the column. The new tapping elevation shall still cover the LLL of the operating range.
10 | Cloud+ | Ahmed Marhoon | Direction to North, is it applicable for this drawing? If applicable, is it shown at the right direction? Otherwise, delete from the drawing. Typical for similar drawing.