## 019-E-DAT-00041-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | 2HCU ( apply to all sheets)
2 | Callout | 1 | Mohamed Ayyash | General comment: Text font is too small, some is not visable. Please enlarge text font to make it readable
3 | Callout | 1 | Mohamed Ayyash | Delete c
4 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all document
5 | Text Box | 2 | Hasan Asad | Fan and driver lubrication points to be extended to the platform level.
6 | Cloud+ | 2 | A.Jabbar Mahmood | We assume that revised design inlet temp is based on TR calculation assuming complete by-pass of E1902. Confirm
7 | Cloud+ | 2 | Yousif Ahmadi | Per FEED document Nozzles are 2. Check and confirm
8 | Cloud+ | 2 | Jawad Alawi | Tubes and header material CS basis temp <450 in FEED
9 | Cloud+ | 4 | A.Jabbar Mahmood | Note 5: correct pump number to P0013A/B as per the new numbering
10 | Text Box | 4 | Hasan Asad | If any FAN to be shutdown due to operational requirement, it shall be equipped with anti rotation mechanism.
11 | Text Box | 4 | Sankara | Fan motors shall be suitable for the relevant hazardous area classification and shall conform to BMPS-P18: Typical
12 | Text Box | 4 | Mahdi Ali | Use Bapco number. Do not use FEED number
13 | Call-out | 4 | Ahmed Marhoon | In addition to the alarms, Control will also be done in DCS. Note 14 to be modified to reflect this function. Typical comment for Fin Fans with Variable Speed Drives.
14 | Call-out | 4 | Mahdi Ali | 019P0013A/B
15 | Cloud+ | 4 | Yousif Ahmadi | Delete Note 17. The same is applicable for all DATA SHEETS
16 | Text Box | 4 | A.Jabbar Mahmood | Note 10 of the FEED D/S regarding the minimum number of fans per bay is missing!
17 | Cloud+ | 4 | A.Jabbar Mahmood | Note 11: correct equipment number to 019E0028 as per the new numbering