## 019-E-DAT-00047-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all document
2 | Callout | 1 | Mohamed Ayyash | Delete c
3 | Callout | 1 | Mohamed Ayyash | Typo
4 | Callout | 1 | Mohamed Ayyash | 2HCU ( apply to all sheets)
5 | Callout | 1 | Mohamed Ayyash | General comment: Text font is too small, some is not visable. Please enlarge text font to make it readable
6 | Call-out | 2 | Sameer Foujdar | No of Passes is 8 as per FEED to be confirmed.
7 | Text Box | 2 | Hasan Asad | Fan and driver lubrication points to be extended to the platform level.
8 | Call-out | 2 | Sameer Foujdar | Inlet Operating pressure is 163 psig as per FEED D/S and Stream data
9 | Text Box | 3 | Mahdi Ali | Use Bapco number. Do not use FEED number
10 | Text Box | 3 | A.Jabbar Mahmood | Note 9 of the FEED D/S regarding the minimum number of fans per bay is missing!
11 | Text Box | 3 | Sankara | Fan motors shall be suitable for the relevant hazardous area classification and shall conform to BMPS-P18 : Typical
12 | Cloud+ | 3 | A.Jabbar Mahmood | Note 5: correct pump number to 019P0011A/B as per the new numbering
13 | Call-out | 3 | Mahdi Ali | 019P0011A/B
14 | Text Box | 3 | Hasan Asad | If any FAN to be shutdown due to operational requirement, it shall be equipped with anti rotation mechanism.
15 | Call-out | 3 | Ahmed Marhoon | In addition to the alarms, Control will also be done in DCS. Note 8 to be modified to reflect this function. Typical comment for Fin Fans with Variable Speed Drives.