## 019-F-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | All other datasheets which have been issued so far, does not have a border. A single format should be followed for all datasheets.
2 | Call-out | 1 | Mahdi Ali | Unit number shall not have prefix
3 | Text Box | 1 | MAK | Use the latest cover page template that is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate.
4 | Text Box | 2 | A.Jabbar Mahmood | General: 1- TR to retain the grid lines for better presentation and to facilitate the understanding of the datasheets. 2- Decimal points shall be used as decimal separator and commas for as thousand separator to avoid confusions
5 | Cloud+ | 2 | A.Jabbar Mahmood | The reported inlet and outlet pressures are significantly higher than those in the FEED D/S. TR to provide the basis for this change and consult with CLG.
6 | Cloud+ | 2 | A.Jabbar Mahmood | 0.355 as per FEED D/S
7 | Cloud+ | 2 | A.Jabbar Mahmood | 0.355 as per FEED D/S. Also remove the negative sign.
8 | Cloud+ | 3 | A.Jabbar Mahmood | The inlet pressures for the superheating coils are 85 psig as per FEED D/S. If this is not a typo, the pressure drop across the coil will be excessively high (110-75). TR to check and confirm
9 | Call-out | 7 | Ahmed Bucheeri | Provide basis of selection
10 | Call-out | 8 | Ahmed Bucheeri | Provide basis of selection
11 | Cloud+ | 9 | A.Jabbar Mahmood | Much higher than the one reported in the design FEED D/S (higher by 171 psi). TR to advise the basis
12 | Call-out | 9 | A.Jabbar Mahmood | Not attached yet in the MR. TR to ensure that this drawing is attached.
13 | Call-out | 9 | A.Jabbar Mahmood | Not attached yet in the MR. TR to ensure that this drawing is attached.
14 | Text Box | 9 | Hasan Asad | Maintenance manual shall provide detailed work procedure for each maintenance activity.
15 | Cloud+ | 10 | A.Jabbar Mahmood | Typo: EPC.
16 | Cloud+ | 10 | A.Jabbar Mahmood | What does the fuel skid refer to...fuel gas KO drum? clarify.
17 | Cloud+ | 10 | A.Jabbar Mahmood | According to the P&IDs, each cell shall be provided with its own analyzers.
18 | Cloud+ | 10 | A.Jabbar Mahmood | The liquid phase (feed oil) should not have H2S. TR to advise the basis of this number.
19 | Call-out | 10 | A.Jabbar Mahmood | Reference shall be made to this note within the datasheet
20 | Call-out | 10 | A.Jabbar Mahmood | (Max/Norm/Min)
21 | Cloud+ | 10 | A.Jabbar Mahmood | Typo: Design
22 | Text Box | 12 | A.Jabbar Mahmood | General for Heat Curve tables: The inlet operating pressures have been increased from the FEED and the given heat curve data do not cover the revised pressure range. CLG shall be requested to provide updated heat curve data.