## 019-G-DAT-00004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Isamu | Delete
2 | Call-out | 1 | MAK | NO. HYDROCRACKING UNIT or 2HCU for short format. This change shall be reflected globally.
3 | Call-out | 1 | MAK | General Comment: Remove any prefixes in front of the Unit Nos.
4 | Text Box | 1 | Hasan Asad | Sundyne High speed high pressure, horizontal, two stages with John Crane seal is required for this application. The Vendor/Supplier shall also provide LCCA for 20 years to understand the maintenance and inspection requirement.
5 | Cloud+ | 2 | A.Jabbar Mahmood | The licensor estimated the NPSHa as 127 ft. Check and update.
6 | Cloud+ | 2 | A.Jabbar Mahmood | Ensure compliance with BMPS A1. Assumed pressure drop from/to unit B.L will need to be verify during detailed engineerin
7 | Cloud+ | 2 | A.Jabbar Mahmood | TR to advise the basis for this number
8 | Callout | 3 | Isamu | RF not suitable for very high pressure. Revise to RJ
9 | Callout | 3 | Isamu | For high speed pumps, light turbine oil or ATF is normally used. Please leave this blank for the Vendor to indicate,
10 | Callout | 4 | Adnan Alothman | Mounting of Seal Support System to be checked against relevant standard.
11 | Text Box | 5 | Hasan Asad | Yes
12 | Text Box | 5 | Hasan Asad | WIT
13 | Callout | 5 | Yousif Ahmadi | Inspection required for connection welds - PT "YES"
14 | Callout | 5 | Yousif Ahmadi | Inspection required for castings - PT "YES"
15 | Callout | 7 | Isamu | NPSHR test shall be carried out for 5 points as with flow rate of the pump and curve shall be plotted with Q-H curve and submitted with the proposal
16 | Call-out | 7 | Mahdi Ali | All references shall be made to Bapco numbers. Do not use FEED numbers
17 | Text Box | 7 | Hasan Asad | 1.Owner standardized on John Crane mechanical seal with a long term contract for reliability services, seal repair and test and supply of inventory. Owner preference is John Crane due to standardization and seal spare interchangeability. 2.The seal API plan shall be accessible and a filling cart is provided for filling the seal pot.
18 | Call-out | 7 | A.Jabbar Mahmood | We assume this is based on the "continous" water injection rate. Confirm and indicate in the note accordingly.
19 | Text Box | 8 | Sankara | Delete Ex p