## 019-G-DAT-00009-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | A.Jabbar Mahmood | General to all pumps: Owner has not received the hydraulic calculations and hence cannot verify the revised pump head and design conditions.
2 | Callout | 1 | Mohamed Ayyash | 2HCU (apply on all sheets)
3 | Text Box | 1 | A.Jabbar Mahmood | General: Use a decimal point instead of a comma as a decimal separator.
4 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
5 | Text Box | 1 | Hasan Asad | The below points are applicable for 019P0020A/B/C, 019P0021A/B and 019P0011A/B attached herein with this transmittal: 1.Instrument for bearing pump/bearing vibration and bearing temperature shall be as per Machinery Monitoring Instrument Table (doc. No. 2520-z000-NM-1515-03-A) and JV rotating equipment criticality assessment. 2.Mechanical seal selection shall be in accordance to Seal OEM selection chart and High Consequence Pump criteria as specified in BMPS G9 shall be considered as well. 3.Bearing life shall be calculated and provided. 4.Complete unit test requirement shall be selected case by case. 5.Owner standardized on John Crane mechanical seal with a long term contract for reliability services, seal repair and test and supply of inventory. Owner preference is John Crane due to standardization and seal spare interchangeability. 6.The seal API plan shall be accessible and a filling cart is provided for filling the seal pot. 7.Close clearance metalized carbon throat bushing for optimal control of stuffing box pressure (Pump Vendor to advice). 8.Labyrinth bearing housing isolators suitable for oil mist system.
6 | Callout | 1 | Isamu | Delete
7 | Text Box | 1 | A.Jabbar Mahmood | TR to note that the optimum number of pumps (two vs. three) and the capacities of these pumps will need to be finalized during EPC in view of the expected operating requirement (the same applies to the Light Naphtha pumps). This issue is included in the P&IDs issue log for evaluation.
8 | Callout | 2 | Mohamed Ayyash | Should read 2/12 ( apply to all sheets)
9 | Call-out | 2 | A.Jabbar Mahmood | As per BMPS A1, the return pressure is 36 psig at unit B.L. Verify
10 | Callout | 2 | Mohamed Ayyash | Overlap with table lines. move back
11 | Call-out | 2 | A.Jabbar Mahmood | As per BMPS A1, the supply pressure is 65 psig at unit B.L. Verify
12 | Callout | 3 | Mohamed Ayyash | Overlap (Hidden text)
13 | Callout | 4 | bapco-user | Mounting of Seal Support System to be checked against relevant standard.
14 | Callout | 5 | Mohamed Ayyash | Overlap with table. use the 2nd line
15 | Text Box | 6 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. All applicable BMPS-J series to be referenced (such as J2, J3 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. 6. Supplier to be notified on consideration of the Permissive (linked to level and MOVs status) requirement per the PID. 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 17. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
16 | Call-out | 7 | Sameer Foujdar | Relative humidity is in the range of 40/88%
17 | Call-out | 7 | Sameer Foujdar | Total no of motors required will be three not two.
18 | Cloud+ | 8 | A.Jabbar Mahmood | This value seems too low. Check
19 | Cloud+ | 8 | A.Jabbar Mahmood | correct typo
20 | Text Box | 8 | A.Jabbar Mahmood | Note 9 of the FEED D/S is missing, with regards to the minimum spillback requirements. This note shall be included.
21 | Call-out | 8 | A.Jabbar Mahmood | Add the rest of note 2 in FEED D/S "Two pumps in parallel operation are required for Max Naphtha cases and only one pump is required for normal Naphtha production"
22 | Cloud+ | 8 | A.Jabbar Mahmood | This value seems too high for Naphtha. Check
23 | Text Box | 8 | A.Jabbar Mahmood | Note 10 of the FEED D/S is missing and shall be included.