## 019-H-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | This is not a mechanical data sheet!
2 | Text Box | 1 | A.Jabbar Mahmood | Use decimal points instead of commas as decimal separators to avoid confusions
3 | Cloud+ | 2 | Adnan Alothman | MR code number is 000-H-MRQ-70001-001
4 | Callout | 2 | Adnan Alothman | FEED Data Sheet shows temperature of Vacuum side as 275 deg. F. To be verified
5 | Cloud+ | 2 | Adnan Alothman | Inlet and Min. Outlet pressures to be verified and check against FEED Data Sheet
6 | Cloud+ | 2 | A.Jabbar Mahmood | The estimated ejector inlet pressure during FEED was 1.8 inHg corresponding to a dryer inlet pressure of 2 inHg as specified by CLG. 1.97 inHg seems to be too tight leaving almost no margin for pressure drop across the dryer and pipes. TR to re-check
7 | Cloud+ | 2 | A.Jabbar Mahmood | needs to be verified against the selected pump shut-off pressure
8 | Text Box | 3 | Mahdi Ali | remove space between sequence number and suffix
9 | Text Box | 3 | Mahdi Ali | 019C0012
10 | Text Box | 3 | Mahdi Ali | Include Unit number
11 | Callout | 3 | Mohamed Ayyash | STREAM ARROW TO BE SHOWN LARGER AND DARK
12 | Callout | 3 | Mohamed Ayyash | DISTANCE LINES ARROWS TO BE SHOWN SMALLER
13 | Callout | 3 | Mohamed Ayyash | Add an arrow here
14 | Call-out | 3 | Sameer Foujdar | As a general comment the new numbering system to be used for all the equipments shown in the drawing.
15 | Call-out | 3 | A.Jabbar Mahmood | correct the equipment number to 019V0017
16 | Call-out | 3 | A.Jabbar Mahmood | correct the equipment no. to 019V0015
17 | Call-out | 3 | A.Jabbar Mahmood | 019P0015A/B
18 | Call-out | 3 | A.Jabbar Mahmood | 019P0016A/B
19 | Callout | 4 | Mohamed Ayyash | 019C0012
20 | Call-out | 4 | Sameer Foujdar | Vendor to provide Operating Guidelines.
21 | Cloud+ | 4 | bapco-user | Destination of Spillback to be checked and confirmed
22 | Call-out | 4 | Sameer Foujdar | As a general comment the new numbering system to be used for all the equipments in the table.
23 | Call-out | 4 | Sameer Foujdar | As a general comment the new numbering system to be used for all the equipments shown in the table.
24 | Call-out | 4 | A.Jabbar Mahmood | 1.9e+31
25 | Call-out | 4 | A.Jabbar Mahmood | 1.9e+32
26 | Cloud+ | 4 | A.Jabbar Mahmood | TR to verify the required elevation
27 | Text Box | 5 | Sankara | Relevant Electrical Specifications shall be included if there area any electric motors / loads in the package
28 | Callout | 5 | Mohamed Ayyash | move to align in front
29 | Callout | 5 | Adnan Alothman | Add " - " to be read -10 psig
30 | Call-out | 5 | A.Jabbar Mahmood | Since the equipment can potentially be subjected to vacuum conditions, consideration shall be given for designing full vacuum (-14.7 psig).