## 019-K-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
| Callout | 1 | Isamu | Delete
| Text Box | 1 | A.Jabbar Mahmood | General: Use decimal points instead of commas as a decimal separator to avoid confusions
| Callout | 1 | Mohamed Ayyash | Delete c
| Text Box | 1 | Ahmed Marhoon | The following are comments related to instrumentation and control: 1. All applicable BMPS-J series to be referenced (such as J2, J3, J6, J31 …etc) for the supplier to comply with. For anti-surge system, BMPS-J16 and for turbine Speed Governor, BMPS-J18 to be referenced for compliance. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Anti-surge arrangement/design shall be reviewed and confirmed with the supplier taking into account the specific technical requirements covered in BMPS. 6. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 7. Requirement of MCM to be detailed with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 8. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 9. All the BN machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 10. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 11. Assistance and involvement of the vendor during CHAZOP/Hazop workshops/studies to be considered. 12. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 13. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 14. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 15.Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
| Text Box | 1 | A.Jabbar Mahmood | Owner has not received the hydraulic calculations of the HP Circuit and hence cannot verify the revised compressor head and discharge design conditions.
| Callout | 1 | Mohamed Ayyash | 2HCU (apply on all sheets)
| Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
| Stamp | 1 | Raj
| Cloud | 1 | Mohamed Ayyash
| Text Box | 1 | A.Jabbar Mahmood | This datasheet shall be reviewed and approved by the licensor
| Cloud+ | 2 | A.Jabbar Mahmood | The discharge pressures are significantly higher than that reported in the FEED D/S and Licensor D/S. The difference is about 100 psi for the normal DC SOR case. Owner needs to understand the reason for such big discrepancy in the hydraulics. TR to clarify and provide the hydraulic calculations for the owner and licensor review.
| Call-out | 2 | Sameer Foujdar | Ensure the following properties are required; if yes some valves to be provided in the data sheet for reference.
| Text Box | 4 | Hasan Asad | Rotor is flexible and high speed balancing is required.
| Call-out | 6 | Sameer Foujdar | To check and confirm orientation is from top or from bottom.
| Text Box | 6 | Hasan Asad | Yes. Compressor NDE side.
| Text Box | 8 | Hasan Asad | N2 Pressurized
| Text Box | 8 | Hasan Asad | Troubleshooting Manual
| Text Box | 8 | Hasan Asad | The vendor shall provide LCCA report for compressor, turbine, DGS, bearings, lube oil system, etc.
| Call-out | 8 | Sameer Foujdar | Supplier to include Operating Manual.
| Text Box | 8 | Hasan Asad | Vendor to advise
| Text Box | 8 | Hasan Asad | WIT
| Text Box | 9 | Hasan Asad | The Dry Gas System shall be JC (only AVL) and the filtration system should be equipped with auto drainage facility - Lesson learnt from Owner facility.
| Call-out | 9 | Sameer Foujdar | 550# Steam operating pressure is 510/540/550 psig & 60# steam operating pressure is 60 psig as per BMPS A1
| Cloud+ | 9 | A.Jabbar Mahmood | The minimum operating CW supply pressure is 65 psig at unit B.L as per BMPS A3. Check and verify
| Call-out | 9 | A.Jabbar Mahmood | Consider adding "The seal system shall be capable of withstanding the maximum settling out pressure following a compressor trip"
| Cloud+ | 9 | A.Jabbar Mahmood | The minimum operating CW return pressure is 36 psig as per BMPS A3. Check and verify
| Call-out | 9 | A.Jabbar Mahmood | Add "Supplier to advise variation in discharge pressure"