## 021-E-DAT-00001-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | General Comment: please refer to BMPS-A8 Section 4.5.1: do not indicate figures in european style (which uses commas for decimal points and periods for thousands separators), use UK/US style with periods for decimal places and commas for thousands separators. check and correct all figures
2 | Text Box | 1 | Ali Kadhem | General Comment – Applicable for some other air coolers: As per UOP EDP datasheet, inside (tube) fouling resistance (0.0020 F.ft2.h/Btu) and air side fouling resistance of (0.0020 F.ft2.h/Btu) were used. However, in this datasheet, air side fouling resistance was not mentioned. Please clarify and include.
3 | Text Box | 1 | Ali Kadhem | Number of passes in the FEED datasheet was specified as 2, however in this datasheet was changed to “ODD”. Please provide the rationale for this change as a note in the datasheet. Please refer also to Bid Query T1266. Please add the below note in the datasheet: "Odd pass arrangement to be provided to keep the inlet and outlet connections are at opposite ends of the cooler to facilitate the structural support of the inlet and outlet manifolding and associated piping”
4 | Text Box | 1 | Ravi Kumar | Refer Bid Query T1266, add a Note in the datasheet "For coolers with a design pressure greater than 1000 psig, the tube-pass arrangement shall be such that the inlet and outlet connections are at opposite ends of the cooler to facilitate the structural support of the inlet and outlet manifolding and associated piping" per BMPS-E7 criteria
5 | Call-out | 2 | Ali Kadhem | To be written as "1.857"
6 | Call-out | 2 | Ali Kadhem | To be written as "2.533"
7 | Call-out | 2 | Ali Kadhem | As per H&MB, the total fluid flowrate for design EOR case is 128120 lb/hr which is higher than design SOR that has been used as the design basis for the air cooler. Please confirm that the duty/surface area required for design SOR is higher.
8 | Text Box | 4 | Sankara | Indicate applicable Hazardous Area Classification for the electric motors: Typical