## 021-E-DAT-00003-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | General Comment: please refer to BMPS-A8 Section 4.5.1: do not indicate figures in european style (which uses commas for decimal points and periods for thousands separators), use UK/US style with periods for decimal places and commas for thousands separators. check and correct all figures
2 | Text Box | 1 | Ali Kadhem | General Comment – Applicable for some other air coolers: As per UOP EDP datasheet, inside (tube) fouling resistance (0.0020 F.ft2.h/Btu) and air side fouling resistance of (0.0020 F.ft2.h/Btu) were used. However, in this datasheet, air side fouling resistance was not mentioned. Please clarify and include.
3 | Call-out | 2 | Ali Kadhem | This seems to be for the "Layout"
4 | Text Box | 4 | Ali Kadhem | As per the EDP datasheet, please consider adding the following note: "Bundle arrangement requirement, limit number of tube bundles to 2, 4, 8, 16 ..... 2nth.
5 | Text Box | 2 | Jawad Alawi | killed
6 | Text Box | 2 | Jawad Alawi | Killed
7 | Text Box | 1 | Ravi Kumar | TTSJV to include Bid Query clarifications T139 and T1866 into the datasheet notes where applicable and confirm.
8 | Text Box | 1 | Ravi Kumar | Refer Bid Query T1850, one of the Bidders mentioned the size of the cooler has to be increased since FEED datasheet design was found under surface. TTSJV to clarify whether the sizing basis and surface area requirements have been checked prior to issuing this datasheet