## 021-H-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 8 | Ali Hasan | Add a Note: the instrumentation shown in the sketch are preliminary. Detailed review for vacuum package instrumentation shall be discussed with the package supplier during the design review meeting.
2 | Call-out | 3 | Ali Kadhem | As per EDP Datasheet the water side design pressure is 165 psig. Please check and confirm.
3 | Call-out | 3 | Jawad Alawi | Confirm material type for TS and Channel
4 | Call-out | 3 | Rashed Almudahka | Inlet pressure for BMP cooling tower is 65psig as per BMPS-A1. Please clarify.
5 | Call-out | 2 | Ali Kadhem | JV to request the process licensor (UOP) to provide clarifications for the following: 1.The rationale for providing two ejectors for each stage, one sized for 100% and other one only for 50%. 2.In case the first stage ejector with 100% capacity is taken out of service, and the ejector with 50% capacity is placed in operation, what will be the water content in the product diesel at design feed rate.
6 | Text Box | 3 | Jawad Alawi | killed
7 | Call-out | 7 | Ali Kadhem | Please provide the rationale for deleting note no.10
8 | Call-out | 7 | Ali Kadhem | Please provide the rationale for deleting note no.23