## 036-A-BOD-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | This document shall be given a common Unit No. 000 because it's applicable to more than one Unit.
2 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. SOC shall coordinate with JV Directorate.
3 | Callout | 4 | balagangadhar.k | Incinerator
4 | Call-out | 4 | MAK | Unit Nos. shall be 3 digits, e.g. 036/037
5 | Text Box | 4 | balagangadhar.k | Unit (SWS)
6 | Text Box | 4 | balagangadhar.k | Units (ARUs)
7 | Callout | 4 | Syed Ahmed | change to mg/Nm3 at all places
8 | Callout | 4 | BD Mori | Separate the paragraph for each unit.
9 | Callout | 4 | Salman Jaffer | No.3
10 | Callout | 4 | balagangadhar.k | Use "TPD"
11 | Callout | 4 | Syed Ahmed | No.3
12 | Callout | 4 | BD Mori | in Sulphur Plant
13 | Callout | 4 | Syed Ahmed | both Hydrogen Plants no.3 and 4 (Unit 098/099) and
14 | Call-out | 4 | MAK | What is the Bapco doc no.?
15 | Callout | 5 | balagangadhar.k | Refer BMPS-A1 for UOM, removing this table or copy the table from BMPS-A1
16 | Call-out | 5 | Hasan Al Noaimi | Recovery
17 | Call-out | 5 | Ali Abbas | Process Level Measurement in %
18 | Text Box | 5 | balagangadhar.k | TPD
19 | Call-out | 5 | Ali Abbas | @ STP for DCS reading
20 | Call-out | 8 | MAK | BMPS-A1
21 | Callout | 8 | Dowon Pyun | This is minimum value
22 | Callout | 8 | Robert.Kawitzki | SSE
23 | Callout | 8 | balagangadhar.k | Remove psia, as it is duplicated
24 | Callout | 8 | Joon Cho | Referring section 6.1 BMPS-A1, this max. wind speed shall be defined as environmental design and 59 ft/s (35 Knots) is for berthing big vessels at all berth therefore it shall be confirmed
25 | Callout | 9 | Salman Jaffer | Incinerators
26 | Callout | 9 | Salman Jaffer | Please rewrite to: The degassed Sulphur flows into the storage section of the sulphur pit over a weir. The storage section capacity is 3 days. The degassed sulphur is then pumped to 1&2SHFs by the Sulphur Transfer Pumps
27 | Callout | 9 | Salman Jaffer | SRUs
28 | Callout | 9 | BD Mori | The sweet Khuff gas is supplied to 3 and 4 Hydrogen Plants as feed and the refinery fuel gas header.
29 | Callout | 9 | Salman Jaffer | section
30 | Call-out | 9 | Hasan Al Noaimi | to SHF1and SHF2
31 | Callout | 9 | Salman Jaffer | Modify it to: from 7CDU/VDU, 1&2SGP, future DCU, 2&3ARU, 2&3BAGRU, 3&4TGTU
32 | Text Box | 9 | balagangadhar.k | Incinerator
33 | Callout | 9 | Salman Jaffer | Khuff Gas
34 | Callout | 9 | Salman Jaffer | Amine
35 | Callout | 9 | Salman Jaffer | less than
36 | Callout | 10 | BD Mori | Add a separate section to describe the capability of BMP Sulfur block unit to process steams from the exiting refinery units considered at FEED stage.
37 | Callout | 10 | Salman Jaffer | Delete Sea
38 | Text Box | 10 | Sankara | Typical Comment applicable for all kWh: Specify the duration. Is it per hour or day etc.?
39 | Callout | 10 | BD Mori | Add separate section to describe details of the common equipment/facilities shared by different units and design consideration for the common facilities.
40 | Callout | 10 | balagangadhar.k | Provide CW consumption, there is one CW cooler in the unit.
41 | Callout | 10 | Salman Jaffer | Incinerator
42 | Callout | 12 | balagangadhar.k | Provide fuel gas consumption
43 | Callout | 12 | balagangadhar.k | SRU/TGTU are net steam producer, why consumption is indicated here
44 | Callout | 12 | BD Mori | This note is not relevant here.
45 | Callout | 12 | Salman Jaffer | mg/Nm3,
46 | Callout | 12 | balagangadhar.k | Use "TPD"
47 | Text Box | 13 | Nalini Mohan | Design life details for piping and heat exchanger bundles not matching with BMPS-A1
48 | Callout | 13 | balagangadhar.k | BMPS-A1
49 | Callout | 14 | BD Mori | On "HOLD" till completion of SGP design
50 | Callout | 14 | Salman Jaffer | Include Rich Amine stream from 1HRU. Refer to stream (21) of 1HRU FEED PFD (BRB-228346 sheet 1 of 3). The stream data shall be updated after completion of 1&2SGPs and 1HRU design.
51 | Callout | 14 | BD Mori | Provide a note to indicating the stream number is from which unit?
52 | Callout | 14 | balagangadhar.k | 1&2SGP
53 | Callout | 15 | BD Mori | Provide a note to indicating the stream number is from which unit?
54 | Text Box | 15 | balagangadhar.k | USgpm
55 | Callout | 16 | Salman Jaffer | 1&2SGPs
56 | Text Box | 16 | balagangadhar.k | USgpm
57 | Callout | 16 | BD Mori | On "HOLD" till completion of SGP design
58 | Callout | 16 | BD Mori | The traces of impurities included in the original design basis are deleted in this table. It is an important information. Therefore, to be incorporated in this table.
59 | Callout | 16 | Salman Jaffer | 7CDU/VDU
60 | Callout | 17 | BD Mori | This unit design capacity is 125 MMSCFD. What is the rationale for 119 MMSCFD value here?
61 | Call-out | 17 | MAK | What is the Bapco doc no.?
62 | Callout | 17 | BD Mori | On "HOLD" till completion of SGP design
63 | Callout | 18 | BD Mori | The traces of impurities included in the original design basis are deleted in this table. It is an important information. Therefore, to be incorporated in this table.
64 | Callout | 19 | balagangadhar.k | Sweet Khuff
65 | Callout | 20 | BD Mori | all mg/Nm3
66 | Callout | 21 | Salman Jaffer | Include Rich Amine from 1HRU
67 | Text Box | 22 | Nalini Mohan | Design Temperature and Pressure should be in line with BMPS-A3
68 | Callout | 22 | BD Mori | This stream design pressure shall be selected based on the highest expected pressure at the battery limit of BAGRU, which is dependent on the Khuff gas supply pressure. Refer Kuhff gas BOD.
69 | Call-out | 23 | MAK | BMPS-A1
70 | Callout | 23 | BD Mori | Source of Hydrogen is from 3 and 4 H2 Plants. During HUB-1, when 3 and 4 H2 Plants are shutdown, what will be the source of H2 3 & 4 TGTUs? Alternate source is required and this stream design pressure shall be based on the alternate Hydrogen source pressure.
71 | Call-out | 24 | MAK | BMPS-A1
72 | Callout | 24 | BD Mori | Composition of these streams shall be revised after completion of SPG unit design.
73 | Callout | 25 | BD Mori | NIL
74 | Callout | 25 | BD Mori | CO +CO2 10
75 | Callout | 25 | BD Mori | add "vppm"
76 | Callout | 25 | BD Mori | 3.5
77 | Callout | 25 | BD Mori | 5
78 | Callout | 26 | Sankara | The information shown in this table is incorrect. Follow BMPS- P1, Clause 5.1.2, Page 12 /56, for the correct voltage splits.