## 036-E-DAT-00001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
2 | Callout | Page 1 | Salman Jaffer | Insert unit name
3 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs
4 | Text Box | Page 1 | Dowon Pyun | Typical comments to all; 1. Contractor shall recheck the philosophy of process temperature control per each item considering the minimum requirement of para. 7.8 in BMPS-A3 and reference project P&IDs. Except for air coolers controlled by VSD, Contractor to confirm which of auto variable fan pitch and louvers are required for temperature control. 2. For the items under wet H2S service and not applied for HIC material, Contractor is required to confirm H2S dissolved partial pressure and the requirement of NACE MR0103. 3. No exchangers have applied for tube to tubesheet joint with seal or strength welds. Contractor to confirm his basis whether this requirement is applicable or not for sour services, hydrogen service, high temperature and high pressure services. 4. Line connection sizes shall be verified by mechanical in connection with fluid velocities in tubes and header boxes.
5 | Cloud | Page 2 | Mahdi Ali
6 | Callout | Page 2 | Salman Jaffer | Specify the thickness
7 | Cloud+ | Page 2 | Saeed Taher | Refer to T1568 for tubes material
8 | Cloud+ | Page 2 | Sameer.Ahmed | This length is not as per BMPS-A1 8.2.3
9 | Callout | Page 2 | Jong.Ahn | indicate P&ID number, this comment common for all data sheet
10 | Callout | Page 2 | balagangadhar.k | Provide note for this section Referring to BMPS-A1 & BMPS-E7. Typical for all air cooler datasheets.
11 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the each air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis.
12 | Callout | Page 2 | Nalini Mohan | Replace with "FRP, Tuf-Lite or equivalent". This comment is applicable to all air fin cooler datasheets
13 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
14 | Callout | Page 3 | Salman Jaffer | No need for note1 because 0370E-DAT-00001-001 is already there.
15 | Callout | Page 3 | Salman Jaffer | a) Please refer to Bid Query T1383 for the requirement for automatic louver b) Type 'B' manifold. c) The degree of the slop for free draining purpose as per PIDs
16 | Callout | Page 3 | Syed Ahmed | 3
17 | Text Box | Page 3 | Hasan Asad | Structure vibration or individual equipment - Limits shall be as per API or ISO.
18 | Callout | Page 3 | BD Mori | Do not use acronyms: Low Severity Wet H2S Service (LSS)
19 | Callout | Page 3 | Julio.Aguilar | add: according to BMPS-A3