## 041-E-DAT-00001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
2 | Callout | Page 1 | Salman Jaffer | Insert unit name
3 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs
4 | Cloud+ | Page 2 | Sameer.Ahmed | As per BMPS-A1 8.2.3, standard tube size O.D. is 25.4 mm (1")
5 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the each air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis.
6 | Text Box | Page 2 | Dowon Pyun | In/Out temperatuers are same. That means no heat exchange. Contractor to confirm this. This comment is typical to 042E4211 & 042E4311.
7 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
8 | Callout | Page 3 | Salman Jaffer | a) Please refer to Bid Query T1383 for the requirement for automatic louver b) Type 'B' manifold. c) The degree of the slop for free draining purpose per PIDs
9 | Callout | Page 3 | Salman Jaffer | Note1 can be deleted as each condenser has a separate data sheet.
10 | Callout | Page 3 | Syed Ahmed | Each header box shall have 1X1.5 inch vent and 1X2 inch drain.
11 | Callout | Page 3 | BD Mori | Follow new unit number