## 041-E-DAT-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | MAK | 041 - NO. 5 SULPHUR RECOVERY UNIT (5SRU)
2 | Callout | 6 | balagangadhar.k | 4" per P&ID
3 | Callout | 2 | balagangadhar.k | 60#
4 | Callout | 9 | balagangadhar.k | A few nozzle sizes are different
5 | Callout | 9 | Sang.Hwang | Add herewith "Para. 19.2.2 Table 1, BMPS-B1"
6 | Callout | 9 | Sang.Hwang | Add note "it has been replaced with note 28".
7 | Call-out | 1 | MAK | Change the equipment no. across this datasheet and all the documents/drawings.
8 | Text Box | 9 | Sang.Hwang | change the exchanger number based new numbering system
9 | Callout | 1 | Syed Ahmed | change the exchanger number to the new number 041E0002
10 | Callout | 9 | Sang.Hwang | change the exchanger number to the new number 041E0002
11 | Callout | 9 | Syed Ahmed | change the exchanger number to the new number 041E0003
12 | Callout | 9 | Syed Ahmed | change the exchanger number to the new number 041E0004
13 | Text Box | 1 | balagangadhar.k | EXCHANGER
14 | Callout | 9 | Sang.Hwang | In case you are willing to indicate applicable specification & relevant para., please add herewith too.
15 | Callout | 9 | balagangadhar.k | No Space
16 | Callout | 9 | balagangadhar.k | No Space
17 | Callout | 9 | Sang.Hwang | Note 21 should be here with red color letter.
18 | Callout | 6 | Sang.Hwang | Note 25 to be added herewith
19 | Callout | 9 | Salman Jaffer | Please check if this document will be given to Vendor
20 | Callout | 3 | BD Mori | Provide the details here
21 | Callout | 9 | Syed Ahmed | Remove s
22 | Callout | 9 | Syed Ahmed | Remove s
23 | Rectangle | 6 | Jong.Ahn | SOC to clarify the instrument connection size as per the section 8 in BMPS-J2, since SOC is discussing with JV further to unify them. This is general comments for all equipment datasheet.
24 | Callout | 6 | Jong.Ahn | SOC to clarify the instrument connection size as per the section 8 in BMPS-J2, since SOC is discussing with JV further to unify them. This is general comments for all equipment datasheet.
25 | Text Box | 1 | Sang.Hwang | This data sheet is not approved because the preceding documents such as MSD has not been submitted. Therefore, Contractor is advised that the Company's comments to be sent this time have not been completed accordingly.
26 | Callout | 2 | balagangadhar.k | This Exchanger is not TEMA type, may use "Special"
27 | Callout | 8 | Salman Jaffer | This note should be given different number to avoid misleading with Note 1 in next sheet.
28 | Text Box | 2 | Sang.Hwang | To be filled up by Contractor
29 | Text Box | 2 | Sang.Hwang | To be specified.
30 | Callout | 3 | Sang.Hwang | Tube pattern shall be indicated exactly.
31 | Text Box | 1 | balagangadhar.k | Typical for all data sheets
32 | Callout | 9 | balagangadhar.k | use 2"
33 | Text Box | 1 | MAK | Use the latest cover sheet which is part of the Homogenization Procedure. SOC shall coordinate with JV Directorate.
34 | Callout | 3 | BD Mori | What is '1' here? Specify.