## 041-F-DAT-00003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | BD Mori | The comments in this document are also applicable to 042E4201 and 043E4301
2 | Stamp |  | Nalini Mohan
3 | Text Box |  | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
4 | Callout |  | Nalini Mohan | Why tube side design temperature is limited to 650degF when it's tubesheet is exposed to 2351degF?
5 | Callout |  | Saeed Taher | Material and ASTM specifications to be specified for all components.
6 | Line |  | BD Mori
7 | Callout |  | BD Mori | A3
8 | Callout |  | BD Mori | Unit shall be consistent with BMPS-A1. This general comment
9 | Callout |  | BD Mori | Add : Licensor thermal rating to be verified by EPC contractor