## 042-A-MSD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Robert.Kawitzki | equipment number as per BMPS-A8 7.2.5.4 - typ comment
2 | Text Box | 1 | MAK | General Comment: Where possible, always align the equipment data block with the respective equipment icon.
3 | Text Box | 1 | MAK | General Comments applies to all MSDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 002 on all the sheets. 3. Always use NTS for MSD scale. 4. Always use A1 for MSD border size.
4 | Callout | 1 | Saeed Taher | Refer to T1099 for CA of steam jacketed pipes
5 | Text Box | 1 | Mahdi Ali | Scale: NTS Size: A1 TTL SHT: 002
6 | Callout | 1 | Nalini Mohan | shall be SS as per FEED datasheet. Typical for other Condensers as well
7 | Callout | 1 | Robert.Kawitzki | text width as per BMPS-A8 - typ comment
8 | Text Box | 1 | balagangadhar.k | Update the process flow scheme as per latest PFD. All Equipment numbers to be updated as per latest equipment list.
9 | Text Box | 1 | Mahdi Ali | Use the latest border
10 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.