## 043-E-DAT-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | MAK | 043 - NO. 7 SULPHUR RECOVERY UNIT (7SRU)
2 | Callout | 9 | Sang.Hwang | add herewith "para. 19.2.2 table 1, BMPS-B1
3 | Callout | 9 | Sang.Hwang | add note "it has been replaced with note 28".
4 | Text Box | 1 | BD Mori | All the comments on this data sheet are applicable to 043-E-DAT-0003-1 and 043-E-DAT-0004-1
5 | Text Box | 1 | Nalini Mohan | As per the agreed workflow, mechanical drawing shall be submitted for static equipment
6 | Callout | 9 | Sang.Hwang | change exchanger number to the new number 043E0004
7 | Call-out | 1 | MAK | Change the equipment no. across this datasheet and all the documents/drawings.
8 | Callout | 9 | Sang.Hwang | change the exchanger number to the new number 043E0002
9 | Callout | 9 | Sang.Hwang | change the exchanger number to the new number 043E0003
10 | Callout | 9 | Sang.Hwang | in case you are willing to indicate applicable specification & relevant para., please add herewith too.
11 | Callout | 4 | Saeed Taher | Material, ASTM specification & grade to be specified
12 | Callout | 9 | Sang.Hwang | note 21 shall be here with red color letter
13 | Callout | 6 | Sang.Hwang | note 25 to be added herewith
14 | Callout | 9 | Salman Jaffer | Please check if this document will be given to Vendor
15 | Callout | 3 | BD Mori | Provide details here.
16 | Text Box | 1 | balagangadhar.k | Refer to the comments provided on identical equipment in Unit 041
17 | Callout | 9 | Syed Ahmed | Remove s
18 | Callout | 9 | Syed Ahmed | Remove s
19 | Callout | 9 | Sang.Hwang | revise it as 041E0002
20 | Callout | 9 | Sang.Hwang | revise it as 042E0002
21 | Text Box | 4 | Saeed Taher | Same comments shall be applied to 043E4303/04
22 | Callout | 6 | Jong.Ahn | SOC to clarify the instrument connection size as per the section 8 in BMPS-J2, since SOC is discussing with JV further to unify them. This is general comments for all equipment datasheet.
23 | Callout | 12 | Jong.Ahn | SOC to clarify the instrument connection size as per the section 8 in BMPS-J2, since SOC is discussing with JV further to unify them. This is general comments for all equipment datasheet.
24 | Callout | 9 | Sang.Hwang | steam design condition shall be specified
25 | Re: Callout | 4 | Sang.Hwang | the heat exchanger type NEN w/integrated t/s. So, t/s gasket is not required. Would you please delete this comment.
26 | Text Box | 1 | Nalini Mohan | This data sheet is not approved because the preceding documents such as MSD has not been submitted. Therefore, Contractor is advised that the Company's comments to be sent this time have not been completed accordingly.
27 | Callout | 8 | Salman Jaffer | This note should be given different number to avoid misleading with Note 1 in next sheet.
28 | Callout | 4 | Saeed Taher | To be filled by contracotor
29 | Text Box | 2 | Sang.Hwang | to be filled up by Contractor
30 | Callout | 2 | Sang.Hwang | to be revised
31 | Text Box | 2 | Sang.Hwang | to be specified
32 | Callout | 3 | Sang.Hwang | tube pattern shall be indicated exactly
33 | Text Box | 1 | MAK | Use the latest cover sheet which is part of the Homogenization Procedure. SOC shall coordinate with JV Directorate.
34 | Callout | 3 | BD Mori | What is '1' here? Specify