## 044-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Are these nos. as per the agreed equipment list?
2 | Callout | 1 | BD Mori | Check the pressure at injection point pressure
3 | Callout | 1 | Salman Jaffer | Delete
4 | Text Box | 1 | Nalini Mohan | For general comments refer to sht 1
5 | Callout | 1 | Salman Jaffer | Modify to: 044P0008B is spare in Warehouse
6 | Callout | 1 | BD Mori | Overlap
7 | Callout | 1 | BD Mori | Provide all chimney tray numbers
8 | Callout | 1 | BD Mori | Provide bed number
9 | Callout | 1 | BD Mori | Provide bed numbers
10 | Callout | 1 | BD Mori | Provide stream data
11 | Callout | 1 | balagangadhar.k | Show the connections properly, show reboiler symbol as per legend
12 | Text Box | 1 | BD Mori | This unit PFDs were prepared during FEED, based on the Licensor EDP PFDs. The PFDs were reviewed by Licensor, Bapco and FEED contractor. The process flow configuration was finalized based on the reviews, Bapco’s operating experience with similar units, lessons learned and industry best practices. The PFDs have also under gone Hazop at EDP and FEED stage. Therefore, the deletion of amine tanks, associated facilities and process modifications, to the FEED stage PFDs are not acceptable. TTSJV shall discuss any changes to the FEED PFDs and P&IDs before it is issued in EPC. TTSJV shall also clearly mark such changes and obtain Owner’s approval. If any PFD and P&ID is issued without Owner’s approval, the transmittal shall be summarily rejected.