## 044-F-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | BD Mori | The changes/additions/deletion done in the FEED documents are not highlighted by TTSJV in the data sheet. It must be highlisted as per the agreed procedure. This comments is applicable to all the data sheets /documents
2 | Callout |  | BD Mori | Comments on this data sheet are also applicable to 045U4501
3 | Callout |  | Nalini Mohan | Modify the tag number as per the latest equipment numbering convention
4 | Callout |  | Mohamed Ayyash | page 1/11 correct all pages
5 | Arrow |  | Jeung.Kim
6 | Text Box |  | Jeung.Kim | All data sheets have to be updated according to FEED Validation and detail design development.- typical comment
7 | Stamp |  | Nalini Mohan
8 | Ellipse |  | Mohamed Ayyash
9 | Callout |  | Mohamed Ayyash | correct page numbers
10 | Callout |  | Syed Ahmed | Sweet
11 | Callout |  | Syed Ahmed | Sweet
12 | Callout |  | Syed Ahmed | Sweet
13 | Cloud |  | Sankara
14 | Text Box |  | Sankara | Modernization
15 | Arrow |  | Sankara
16 | Text Box |  | Salman Jaffer | modify re levent to relevant
17 | Arrow |  | Salman Jaffer
18 | Line |  | BD Mori
19 | Callout |  | BD Mori | Replace with " outlet"
20 | Callout |  | BD Mori | Quantity of nitrogen flow? To be checked with Licensor.
21 | Callout |  | Syed Ahmed | General note to be added: All the equipment and control valves shall be suitably design for all the operating cases for normal and turndown operation.
22 | Text Box |  | Salman Jaffer | Modify CO2 to (CO+CO2) per T334
23 | Arrow |  | Salman Jaffer
24 | Callout |  | BD Mori | Vendor to specify and incorporate incinerator heating and cooling temperature rates for start-up and shutdown
25 | Typewritten Text |  | Mohamed Ayyash | move
26 | Arrow |  | Mohamed Ayyash
27 | Callout |  | Saeed Taher
28 | Callout |  | Saeed Taher | Vendor to propose material selection to be reviewed and approved during EPC phase. This is applicable to the whole incinerator package.
29 | Callout |  | Syed Ahmed | Sweet
30 | Callout |  | Syed Ahmed | Sweet
31 | Text Box |  | Salman Jaffer | Numbering of notes in this document is not consistence, just an example Note 7 is shown in sheet 6 and same number is used in sheet 7. Moreover, note 1 is shown in sheet 6 and another note 1 in sheet 10.
32 | Arrow |  | Salman Jaffer
33 | Arrow |  | Salman Jaffer
34 | Cloud |  | Salman Jaffer
35 | Text Box |  | Salman Jaffer | Some notes could not be found such as notes 12 and 15. Please check the notes and sequence.
36 | Arrow |  | Salman Jaffer
37 | Arrow |  | Salman Jaffer
38 | Text Box |  | Salman Jaffer | Please review the need of maintaining note 18 in this document, sour Khuff gas will not be sent to the Incinerator directly (only treated).
39 | Arrow |  | Salman Jaffer
40 | Callout |  | BD Mori | Revise Fuel gas details as per the latest BMPS-A1
41 | Line |  | BD Mori
42 | Callout |  | BD Mori | Delete
43 | Line |  | BD Mori
44 | Callout |  | Nalini Mohan | As per FEED, No.6 stream is using ejectors with 110# steam
45 | Callout |  | Nalini Mohan | Mode of temperature control should be defined by EPC Contractor.
46 | Callout |  | Mohamed Ayyash | align on all pages
47 | Arrow |  | Mohamed Ayyash
48 | Callout |  | Mohamed Ayyash | N
49 | Arrow |  | Mohamed Ayyash
50 | Arrow |  | Mohamed Ayyash
51 | Arrow |  | Mohamed Ayyash
52 | Arrow |  | Mohamed Ayyash
53 | Arrow |  | Mohamed Ayyash
54 | Callout |  | Mohamed Ayyash | No.
55 | Arrow |  | Mohamed Ayyash
56 | Callout |  | BD Mori | This shall be considered in the down stream equipment and stack design.
57 | Callout |  | BD Mori | 550# steam shall meet the purity specifications provided in BMPS-A1
58 | Line |  | BD Mori
59 | Callout |  | BD Mori | (supply pressure)
60 | Callout |  | Salman Jaffer | Boiler Feed Water control valve and associated bypass shall be designed adequately to ensure that vibration and erosion is prevented.
61 | Typewritten Text |  | Mohamed Ayyash | .
62 | Arrow |  | Mohamed Ayyash
63 | Typewritten Text |  | Mohamed Ayyash | add
64 | Typewritten Text |  | Mohamed Ayyash | .
65 | Arrow |  | Mohamed Ayyash
66 | Typewritten Text |  | Mohamed Ayyash | add
67 | Callout |  | Saeed Taher | This is the minimum requirements, vendor to propose selection of refractory type and thickness to be reviewed and approved during EPC phase.